## ReadMe
Jonathan Langford | [5 empty] | Jonathan Langford
READ ME
| Field Colors |  |  |  | Hide/ Unhide Definitions
| Mandatory field |  | Optional field | Automated field
Text Colors
|  | Black Text: | Purple Text: | Red Text:
| R/A/I/D is due in more than 7 days. |  | R/A/I/D is due within next 7 days. | R/A/I/D is overdue or due today.
Risk Rating Matrix (Basic)
Risk Management Strategy
Note: to change any dropdowns in the RAID tabs, right click and unhide the applicable "Data_" tab.
Jonathan Langford | [5 empty] | Jonathan Langford
Press to (un)hide definitions for how to fill the sections of the tool.

## Dashboard
| Matrix Dashboard | [12 empty] | Actions Dashboard
|  | Risk Matrix (without controls) | [5 empty] | Issues Matrix | [15 empty] | #FFFF00 | #C4D79B | #FCD5B4 | #DA9694
| Impact |  | Very Low | Low | Medium | High | Very High | Impact |  | Low | Medium | High | Very High |  | 4 | Risk Actions Progress |  |  | 3 | Issue Actions Progress |  |  |  | Low | Moderate | Severe | Critical
| Probability | Very High |  |  | 1 | 0 |  | Priority | Very High |  |  | 0 | 1 | [9 empty] | Commercial | 0 | 2 | 1 | 0
|  | High |  |  | 1 | 1 | 5 |  | High |  | 2 | 3 |  |  |  | 3 | Red | 9 |  | 0 | Red | 9 | Data | 0 | 1 | 0 | 0
|  | Medium |  |  | 1 | 1 | 3 |  | Medium |  | 1 | 1 | [10 empty] | Delivery | 1 | 0 | 2 | 0
|  | Low |  | 4 | 4 | 0 |  |  | Low |  | 1 |  |  |  |  | 0 | Amber | 4 |  | 3 | Amber | 4 | Financial | 0 | 5 | 1 | 0
|  | Very Low | [20 empty] | Governance | 0 | 0 | 1 | 3
|  | Risk Matrix (with controls) | [13 empty] | 1 | Green | 2 |  | 0 | Green | 2 | Operations | 0 | 1 | 0 | 0
| Impact |  | Very Low | Low | Medium | High | Very High | [15 empty] | People | 0 | 2 | 0 | 0
| Probability | Very High | [6 empty] | 4 |  | Risk Target date overdue | [11 empty] | Process | 0 | 0 | 0 | 0
|  | High |  | 1 | 1 | 3 | 0 | [15 empty] | Technology | 0 | 1 | 0 | 0
|  | Medium |  |  | 3 | 4 | 0 |  | 8 |  | Issue Target date overdue |  |  |  | 4 | Risk Actions overdue |  |  | 3 | Issue Actions Overdue |  |  |  | 1 | 12 | 5 | 3
|  | Low |  | 4 | 3 | 0 | 0
|  | Very Low | 0 | 1 |  |  | 1 | [7 empty] | 0 | No Target Date |  |  | 0 | No Target Date
Risk and Issue Category Dashboard
| Risk Category | [6 empty] | Issue Category
|  | 3 | Commercial | [5 empty] | 0 | Commercial
|  | 1 | Data | [5 empty] | 2 | Data
|  | 3 | Delivery | [5 empty] | 0 | Delivery
|  | 6 | Financial | [5 empty] | 2 | Financial
|  | 4 | Governance | [5 empty] | 3 | Governance
|  | 1 | Operations | [5 empty] | 1 | Operations
|  | 2 | People | [5 empty] | 1 | People
|  | 0 | Process | [5 empty] | 0 | Process
|  | 1 | Technology | [5 empty] | 0 | Technology
|  | 21 | Total | [5 empty] | 9 | Total

## Risks
Unique Risk ID (should be the functional areas or project's unique 2 or 3 digit suffix, followed by 'R' for 'risk', followed by a unique consecutive number beginning 001 - e.g. R001 | ADO ref for items escalated through project or programme owners | Defines the short name for the risk. Must be a short title by which the risk can be easily recognised and referred, whilst providing some context as to what the risk actually is. | The date this risk has been identified. | The person identified to own and monitor the risk. This person is responsible for verifying that the risk is managed and tracked appropriately through its lifecycle | The person identified with overall responsibiliy for this area of activity. The person to perform an evaluation of the risk. | Specifies the progress of the risk | Displays the category to which the risk belongs. | Specifies who the risk has been escalated too | Description of the risk with sufficient information for one to understand the matter. It should be written clearly, outlining the cause and effect of the risk. | Because of a fact or existing condition, an event may occur, resulting in an impact or consequence to an objective | Detailed impact description of the risk on the project objectives. This should include a description of the impact expected should the risk become and issue, including who would be affected and how. | Event when risk could become an issue | High-level assessment of the financial (including commercial) impact, for example increased cost of delay, Low, Medium or High | Defines the likelihood that a risk will occur: 5:Very High >75%; 4:High 51-75%; 3:Medium 26-50%; 2:Low 6-25%; 1:Very Low 0-5% | Defines the effect of risk on the project / programme objectives: Very Low, Low, Medium, High or Very High | Combined Likelihood/ Impact Calculation is automatic based on the Risk Matrix (found in the first tab) | Slow (impact of the risk would be evident within 1 year), Medium (impact of risk would be evident in 1 quarter), Fast (impact of risk would be evident in 1 month or less) | The amount of risk LI Ltd is willing to accept. Ranges from averse to eager | The approach to managing risk should be specified as one of the following: Treat (management/mitigation actions);Terminate (stop the activity causing the risk); Transfer (pass the risk to a third party); Tolerate (accept the risk without management actions) | Relevant for treat and transfer: Defines risk response plan to mitigate and resolve the risk with target dates. It should capture the final resolution of the matter once it is resolved. It should outline the actions required to mitigate/resolve the risk. | Relevant for treat and transfer: Defines the likelihood that a risk will occur after mitigating actions have been taken: 5:Very High >75%; 4:High 51-75%; 3:Medium 26-50%; 2:Low 6-25%; 1:Very Low 0-5% | Relevant for treat and transfer: Defines the effect of risk on the project / programme objectives after mitigating actions have been taken: Very Low, Low, Medium, High or Very High | Relevant for treat and transfer: Combined residual Likelihood/ residual Impact Calculation is automatic based on the Risk Matrix (found in the first tab) | Relevant for treat and transfer: Assessment of the progress against mitigating the risk. On target (1), caution (2) or not on target (3) | Defines the date the risk is targeted to be resolved. | Defines the actual date the risk is resolved. | Days until the Risk is due (calculated) | Is the Risk already overdue? (Calculated) | Updates on any change of status and the reason. It should highlight recently completed activities to transfer, mitigate or resolve the risk. | Defines the short name for the action that is listed in the resolution/mitigation strategy. | Defines the resource responsible for verifying that the action is managed and tracked appropriately through its lifecycle | Specifies the progress of the Action | Assessment of the progress completing the action. On target (1), caution (2) or not on target (3) | Defines the date the action is targeted to be completed. | Is the Action already overdue? (Calculated) | Defines the short name for the action that is listed in the resolution/mitigation strategy. | Defines the resource responsible for verifying that the action is managed and tracked appropriately through its lifecycle | Specifies the progress of the Action | Assessment of the progress completing the action. On target (1), caution (2) or not on target (3) | Defines the date the action is targeted to be completed. | Is the Action already overdue? (Calculated) | Defines the short name for the action that is listed in the resolution/mitigation strategy. | Defines the resource responsible for verifying that the action is managed and tracked appropriately through its lifecycle | Specifies the progress of the Action | Assessment of the progress completing the action. On target (1), caution (2) or not on target (3) | Defines the date the action is targeted to be completed. | Is the Action already overdue? (Calculated)
[14 empty] | Inherent Risk (without controls) | [6 empty] | Residual Risk (with controls) | [8 empty] | Action 1 | [5 empty] | Action 2 | [5 empty] | Action 3
Risk ID | ADO REF | Risk Name | Date identified | Owner | Domain Owner | Status | Risk Domain Category | Escalation | Description | Causation | Impact Description | Impact Event | Financial Impact | Likelihood (L) | Impact (I) | Risk Rating | Risk Velocity | Risk Appetite | Response Type | Resolution / Mitigation Plan | Residual Likelihood (L) | Residual Impact (I) | Residual Risk Rating | Risk RAGs | Target Mitigation Date | Actual Resolution Date | Days until target date | Overdue? | Latest Update | Action Name 1 | Owner2 | Status2 | Action RAG | Target completion date | Overdue?2 | Action Name 2 12 | Owner 13 | Status24 | Action RAG5 | Target completion date6 | Overdue?27 | Action Name 3 | Owner 14 | Status25 | Action RAG6 | Target completion date7 | Overdue?28
R001 |  | Lack of clarity and strategy on data approach | 2021-04-14 | Stuart McDonagh | Simon Freeman | Open | Data | NA | If there is no agreement on the policy and technical priorities to standardise data sharing at a devolved level and/or there is insufficient governance and delivery capability to ensure that devolved services work in that context | Because there is no agreement for common data standards and formats with the Devolved Administrations and DDTS | 1) Then LI Ltd is not able to deliver replacement services or a comprehensive traceability service at a UK level. 2) LI Ltd data practice is not operating efficiently because it requires considerable time and cost to resolve data issues and maintain data quality. | An outbreak, food safety incident or trade challenge that cannot be adequately managed because of the quality, timeliness or accessibility of traceability data at a UK level. OR Inability to go live with new services. | High | High | Very High | Critical | Medium | Open | Treat | Secure agreement for common data standards and formats with the Devolved Administrations and DDTS as new species come into scope for England multi-species platform and UK View. Provision of data for UK View and share of operational data for cross border moves to be treated separately. LI Ltd have data for UK View but continue to work on ensuring consistency of data for cross border moves. Work being carried out on DSAs by Daniel Meaney (DPO) and Malcolm Dunsmore. | Medium | Medium | Moderate | 1 | 2024-03-31 |  | 193 | No | Action due date moved out as cross border design sessions now taken over by discussions on DDTS integration layer (27/09/2022) 01/11/22: There is a lack of strategy and agreement rather than any regulatory data sharing issues. Incumbent on the ADPG Traceability Group to lead on strategic focus. This risk is at the root of data practice issues within LI because of the time and effort required to wrangle DA data. Need to rate the financial impact much higher. LI cannot solve the DA problem from the bottom up. Action: SF to rearticulate the DA top-down problem as a new issue. 29/11/22: Target date updated to 31/3/23 09/01/23: Actions for DSAs in progress with Daniel Meaney and Malcolm Dunsmore. Will become more critical in the design phase (needs proximity measure) 07/02/23: Liaison with Defra DPO has not provided any further clarity. As a protection LI will produce service agreements and EULA equivalent to assure Li's data compliance and use this output to broker agreement with Defra to streamline the process and standardised documentation. End of March to produce an LI set of documentation. 07/03/23: LITP have now taken responsibility of data risks under the leadership of Roger Goodwin. Reduce residual impact to Medium and risk rating to Severe. 04/04/23: No change. Sits with LITP DA. 27/04/23: Open actions closed because Danny & Mal contribute on behalf of LI through the LITP. 02/05/23: No change. Roger Goodwin is now managing the data aspects. moved from authority down to a cooperative forum and this has enabled a way of dealing with data that doesn’t require command and control centralisation and will generate more progress. Risk will not be fully mitigated until the project has finished all the data. No more opportunity to reduce risk. Residual Likelihood reduced to Medium. | Secure agreement for common data standards and formats with the Devolved Administrations. | Stuart McDonagh | Closed | 2 | 2022-09-27 | Yes | Secure agreement for common data standards and formats with DDTS. | Stuart McDonagh | Closed | 2 | 2022-09-27 | Yes
R002 |  | Implementation of project A delayed | 2021-04-14 | Simon Freeman | Simon Freeman | Open | Delivery | ADPG | There is a risk that the Livestock Information Transformation Programme (LITP) will not complete the design and implementation of BEID and digital passports in a sufficiently timely manner to align with new traceability service delivery. | Because of an uncoordinated approach to implementation planning between LTP and DAs. There is no joint England, Wales, and Scotland commitment to key milestones in the transition plan for the implementation of Bovine EID and/or digital passports. | This will lead to LI having to implement multiple tags (old tags and BEID), both paper and electronic passports, that would cause negative reputational impact for Defra, AHDB and LI Ltd and drive cost into the solution. | When UK plans become clear. When UK admins make decisions on implementation timelines. When UK administrations publish timelines and associated rationale. | High | High | Very High | Critical | Fast | Open | Transfer | 1) LI need Policy to move faster on all aspects of requirements, including BeID, Digital Passports and Automated Moves. 2) Working with the LTP Design Authority on data issues. 3) Awaiting confirmation that all cattle legislation will be complete by March 2024. | Very Low | Low | Low | 1 | 2023-10-30 |  | 40 | No | Originally raised in ADO 37701 24/09/2021. Transferred to strategic risk register. LIP delays DA service implementation. To assess the impact of sprint zero recommendations on planning (04/07/2022) 01/11/22: Needs policy colleagues to move faster to resolve BEID. Frequency LF and UHF and numbering. 29/11/22: Roadmap of legislative changes does not align with delivery plans relating to passports. The requirement to change legislation to alter industry behaviours delays delivery of the multi-species data service to be added as new risk. 09/01/23: Policy have verbally said all cattle legislation complete by March 2024 (including BEID). Risk measure will not change until this is confirmed. 07/02/23: The timeline for BEID and digital passports is unclear. Implications a) burning money b) extending LI delivery timelines c) increasing industry frustration. A possible solution would be to find a way to decouple BEID and digital passports. Residual impact increased to High. 07/03/23: In principle the decision has been taken that LI will need to implement paper passports, therefore the timing of BEID and digital passport rollout is no longer a risk. Residual L and I reduced to Medium. 04/04/23: IH/JA had a demo of BEID. IH to follow up with SRO to suggest the pilot is time boxed to produce evidence for discussion. 02/05/23: Risk has been mitigated because the decision has been made to implement paper passports (BEID and paper passports have been decoupled). Residual Likelihood reduced to Very Low. Residual Impact reduced to Low. | Assess the impact of sprint zero recommendations on planning. | Ian Hewett | Closed | 1
R003 |  | Lack of effective decision-making | 2022-04-08 | Ian Hewett | Ian Hewett | Open | Governance | LI Board | If the decision-making authority is unknown or unclear at the Livestock Transformation Programme Board (LTPB) because Members of the Company (AHDB/Defra) have not clearly defined the Scheme of Delegation. | because Members of the Company (AHDB/Defra) have not clearly defined the Scheme of Delegation. | Then key decisions are slow or cannot be made and LI Ltd is unable to deliver its strategic objectives. Resulting delay in next steps - bEID, Digital Passports and Automated Moves. Members do not agree with the Target Operating Model (as set out in the Delivery Agreement). There is duplication or work of little or no consequence/value. The delegated authorities, accountabilities and responsibilities of LI Ltd's Senior Leadership Team are unclear. The worst case could result in a terminal outcome for the programme or LI Ltd due to the inability to fulfil its strategic objectives. |  | High | High | Very High | Critical | Medium | Minimal | Treat | 1) John Cross and Ian Hewett consider refreshing the GOM and DA after the review of the company's sponsorship model concludes. 2) Prioritise input into the LTPB, focussing on teasing out direction and requirements and establishing an effective working relationship. 3) Ian Hewett presented to the LTPB the decisions required of it and use those to inform learning about who makes what decision and on what basis. 4) Implement findings / recommendations of the task and finish groups. 5) New SRO (Vicky Moore) establishing structure 6) Established regular joint SLT meetings | High | High | Critical | 3 | 2023-05-31 |  | -112 | Yes | 29/11/22: Decision-making and commissioning at LTPB is becoming clearer, however the corporate governance and constitution of LI is under consideration and will not be clear until the company's sponsorship is clarified. 07/02/23: Lack of LTPB delivery timeline. Residual L and I increased to High 07/03/23: No change 04/04/23: Clarity is emerging. The AHDB Board has reached a decision on their future sponsorship of LI Ltd. Awaiting formal confirmation of AHDB intention to reduce their majority shareholding. IH/SK/SF/JC to work through the implications. Vicky Moore has been confirmed as SRO and Paul Caldwell as Sponsor. 02/05/23: Improving situation (new SRO and joint SLT meetings). Remains critical pending further clarity and completion of legalities associated with the AHDB sponsorship change. The LITP Board has recommended setting aside the current set of governance documents and accepting the need for changes whilst the legal requirements are put in place. | Refreshed GOM and DA | Ian Hewett | Open | 3 | 2023-05-31 | Yes | Establish effective working relationship with AHDB | Ian Hewett | Open | 3 | 2023-05-31 | Yes | LI MD prsentation to AHDB | Ian Hewett | Closed | 2
R004 |  | Key permanent staff or any staff with specialist skill leave. | 2022-04-08 | Stuart McDonagh | Zoe Hodgkinson | Closed | People | NA | Key permanent staff or any staff with specialist skill leave. | Because losing key people is inevitable. They may take a new job opportunity, retire, suffer a long-term illness, or die unexpectedly. | Then this may result in a negative impact on operational running and delivery, cost overruns, time delays, and failed procurement due to a lack of resilience. The worst case could result in a terminal outcome for the programme or LI Ltd because of delivery failure. | Loss of key individual | Med | High | Very High | Critical | Medium | Open | Treat | 1) Diversify LI Ltd’s approach to staff recruitment and retention. 2) Manage critical knowledge by documenting activities, identifying others for training and knowledge transfer and undertaking succession planning for key skills. 3) Create a great place to work, a supportive and inspired culture where delivery professionals feel empowered. 4) Undertake skills and services audit and establish the gaps. 5) Development of a new Target Operating Model including a Human Capital Management capability. 6) LI in process of creating baseline set of LI's own corporate HR policies, based on AHDB documentation by 31/03/23 7) Provide LI specific wording to fit into AHDB's templates for JD's 8) Tactically deploying PMO resources across the TOM pillars | High | Very High | Critical | 3 | 2023-06-30 | 2023-05-02 | -82 | Yes | 01/11/22: No change 09/01/23: Situation worsening. Residual Risk increased. Data Director and Finance Director roles still unfufilled. 27/01/23: Situation worsening. Residual Risk increased. Data Director remains unfilled and AHDB/LI are severely impacted by capacity constraints. 07/02/23: Tactically deploying PMO across the BCAs. 07/03/23: Description updated. Residual I increased to Very High. 04/04/23: Potential ramifications of AHDB ownership decision. 02/05/23: Remains Critical to be transferred to the Issue Register I086. | Diversify staff recruitment and retention | Stuart McDonagh | Open | 3 | 2023-06-30 | Yes
R005 |  | Lack of resilience against unexpected disasters and events | 2022-04-08 | Stuart McDonagh | James Hatful/Paul Wills | Open | Operations | NA | If LI Ltd is not prepared for a variety of threat scenarios that lead to damage to, or loss of, key resources or core assets, for example, cyberattacks, data breaches, unplanned IT outages, security incidents, loss of 3rd party location, loss of key personnel. | Because of a lack of effective business continuity planning, preparation and recovery testing for unexpected disasters and events | Then LI cannot restore the Livestock Information Service to a predefined level of operation following a disruption that may fail to deliver the core statutory service or result in a loss of essential data, which affects its reputation negatively. The worst-case could result in a terminal outcome for the programme or LI Ltd. | the failure of software and hardware tools and equipment, would cause LIS to be disrupted or cause entire functioning and performance to fail. Including information security incidents, cyber-attacks, password theft, and service disruptions. | Med | Medium | Very High | Critical | Medium | Minimal | Treat | 1) Complete remaining disaster recovery testing (as per IT Control Audits action) 2) Commission a test of the BCP in early 2023. 3) QA Lead to take lead on progressing a proper level of robustness in documents and policies. Work was initiated to establish criteria for National Infrastructure and Critical National Infrastructure and where LI systems sit in these definitions so we can incorporate appropriate RTO/RPO into the future design. 4a) Current state: COO coordinating BC and DR responses. 4b) Future state: Programme coordinating design and operations activities to ensure the service integration model is correct i.e. that BC, DR, security and monitoring are built in from day one. 5) Appoint a security/cyber partner to reinforce remedial actions | Very Low | Very High | Moderate | 1 | 2023-05-31 |  | -112 | Yes | 01/11/22: JA to take lead on progressing a proper level of robustness in documents and policies. Work was initiated to establish criteria for National Infrastructure and Critical National Infrastructure and where LI systems sit in these definitions so we can incorporate appropriate RTO/RPO into the future design. 29/11/22: Target date updated to 31/3/23 09/01/23: Two pronged mitigation strategy initiated for current and future responses. 07/02/23: Deck for ARAC of business risk being prepared by SF to get the risk into clearer perspective and greatly reduced likelihood of losing 6 data centres. No further mitigation actions required. In light of which Residual L reduced to Very Low. Recommend Risk to be Closed when all relevant documentation is complete. 07/03/23: No change 04/04/23: Three tabletop exercises have been completed across the BCP and recommendations for improvements identified. Procurement of a security/cyber partner will be rerun to increase responses, with target completion end of May (pen test contract has been awarded). 02/05/23: Work in progress and on track. | Complete disaster recovery training | Stuart McDonagh | Open | 1 | 2023-05-31 | Yes | Develop business continuity plan | Stuart McDonagh | Closed | 1 | 2022-08-31 | Yes
R006 |  | Failure to manage key commercial partnerships, and contractual requirements | 2022-04-08 | Stuart McDonagh | Wayne Augur | Closed | Commercial | NA | If LI LTD fails to manage key commercial partnerships and contractual requirements | Because of the lack/loss of commercial expertise in the organisation and/or a lack of Contract Management processes. | Then funding is not approved or does not provide the certainty needed to enter complex commercial agreements. Key contracts reach the end of life without commercial arrangements to extend or renew. The spending trajectory of key contracts exceeds the maximum contract value in place of new commercial arrangements. Which may result in short-sighted commercial decisions, poor performance, inefficiency, poor value for money, fraud, and /or failure to meet business requirements/objectives. |  | High | Medium | Very High | Critical | Medium |  | Treat | Define future sourcing model. Dependency on the findings/recommendations of the task and finish group which informs commercial pipeline and Contract management. Define commercial pipeline Document approach to Contract Management | Low | Medium | Moderate | 1 | 2023-03-31 | 2022-11-08 | -173 | Yes | 01/11/22: Action WA to merge 130/131 into a more generic contract management risk. 09/11/22: Superceded by R150 | Define commercial pipeline | Wayne Augur | Closed | 1 |  |  | Define future sourcing model | Wayne Augur | Closed | 2 |  |  | Document approach to contract management | Wayne Augur | Closed | 1
R007 |  | Delivery partner contracts expire before replacement arrangements are in place | 2022-05-12 | Stuart McDonagh | Wayne Augur | Closed | Commercial | Paul Caldwell (LTPB) | If LI are not able to put suitable new or replacement arrangements in place before current contract expire(s) | Because outputs of the strategic review are awaited and/or funding and spend controls are not yet in place for commitments beyond FY22/23. | Then LI may be forced to extend the current arrangements as a Direct Award which places a risk on continued compliance with the Procurement Regulations and may give rise to an increase in current prices and/or introduction of new terms which may be difficult to successfully mitigate or avoid |  | High | High | Very High | Critical | Fast |  | Treat | 1. Livestock Transformation Programme Board to begin planning now for funding arrangements and spend controls approval for future years. 2. Contracts requiring extension/renewal beyond FY22/23 to be flagged to SRO by LI MD with a recommendation to extend or replace based on current knowledge of delivery landscape. | Medium | High | Severe | 1 | 2023-03-31 | 2022-11-08 | -173 | Yes | 01/11/22: Action WA to merge 130/131 into a more generic contract management risk. 09/11/22: Superceded by R150 | To merge 130/131 into a more generic contract management risk. | Wayne Augur | Closed | 1
R008 |  | Rework of the requirements specification in response to various design reviews | 2022-06-14 | Simon Freeman | Simon Freeman | Closed | Delivery | Paul Caldwell (LTPB) | If LI view of the current specification of requirements for Cattle need to be amended following the outcomes of the strategic review and completion of current Defra cattle design projects. | Because of any findings and recommendations of; a proposed review of LI's technical architecture; an independent assessment of Scot EID; the Cattle working groups; and the task and finish group that are crucial to informing the future direction of LI Ltd development activities. | Then there is a risk that delivery plans will need to be impact assessed and changes made to the delivery scope, timing and priority. |  | High | High | High | Critical | Medium | Open | Transfer | 1) LI Ltd to continue to engage with key stakeholders to secure emerging ensure early view of plans and scope for initial cattle delivery. 2) LI Ltd to continue to take a flexible approach to building the backlog and ensure flexibility within third party contracts to enable re-allocation or termination of resource if required due to a substantive change in requirements and/or direction. | Medium | Very High | Critical | 3 | 2023-04-30 | 2023-05-02 | -143 | Yes | 01/11/22: Action SF to raise a new risk covering the future of LI at the strategic level because either Defra ceases to fund LI or a political decision is taken to close LI (subsumes LI-R132). 29/11/22: No change 09/01/23: LI is progressing with the design work to meet a KPI that has been set on us whilst the wider programme has started a review to decide what the solution could or could not be and the two timelines are not aligned so we run the risk of rework should the work not come to us. 07/02/23: Residual L reduced to Very Low. However in relation to SCOTEID, whilst the independant review has concluded there is still resistance in Defra. IH to take offline with SF. 07/03/23: Reviews still in progress. Target mitigation date moved out 30/04/2023. Residual L increased to medium. Residual I increased to V High (given that LI will have signed off HLD). 04/04/23: No change. Must be resolved by target date 30/04/23 02/05/23: It was agreed at the LITP Board meeting of 26th April that SCOTEID will not be taken forward. Risk Closed. | To raise a new risk covering the future of LI at the strategic level because either Defra ceases to fund LI or a political decision is taken to close LI (subsumes LI-R132). See LI-R151 | Simon Freeman | Closed | 2 | 2022-11-08 | Yes
R009 |  | Obligations under company law | 2022-06-14 | John Cross | Ian Hewett | Closed | Governance | LI Chair | If Members of the Company (AHDB/Defra) are unable to provide a stable board with long-serving and committed members. | Because of the uncertainty surrounding the company’s Ownership and Governance structure. | Then the Board is unable to provide effective governance in relation to its obligations under Company law. Creates risk to the overall control & delivery environment. |  | Low | High | High | Critical | Slow | Minimal | Transfer | Board Chair to escalate to Members of the Company (AHDB/Defra) | Low | High | Moderate | 1 | 2023-03-31 |  | -173 | Yes | 01/11/22: no change 29/11/22: Moving towards more stable Board. Evaluation Assessment likely to highlight other issues. Risk closed because covered by Issue LI-I073
R010 |  | Reputational Damage | 2022-08-30 | Ian Hewett | Ian Hewett | Open | Governance | Paul Caldwell (LTPB) | Industry and wider stakeholder expectations regarding delivery of the multi-species service [platform] are not met. | Because delivery does not proceed at pace or beyond the live sheep service. | Industry, suppliers, and staff loose confidence in the strategy, objectives and plans of the Defra Livestock Information Transformation Programme (LITP) and through that, LI Ltd. Industry support for LI Ltd and the intended outcome wanes. Suppliers disengage and key staff leave. | Failure to secure future funding or go ahead for cattle delivery | High | Medium | Very High | Critical | Fast | Cautious | Treat | 1) Secure future funding from LTPB 2) Secure go ahead for Cattle delivery from LTPB 3) Use communication channels of TDUG and Defra/AHDB sponsors to mitigate any damage caused. | Medium | High | Severe | 2 | 2023-10-31 |  | 41 | No | 06/10/2022: Promoted to Issue following SLT RAID review 06/10/2022 - LI-I079 01/11/22: Reopen risk and close LI-I079 29/11/22: Industry will vote with their feet in the face of a perceived lack of action. 09/01/23: Close to becoming an issue. BEID pilot needs to happen. For credibility LI need to get LUIS for cattle and UK View across the line. What follows is less clear and lacks any clear prioritisation and targets and parts of industry will see this as lack of progress. Likelihood increased to High, increasining residual risk to Severe. 07/02/23: Ongoing risk under review. 07/03/23: Outstanding decision on future funding for development could impact on reputation. Mitigation actions updated. Residual I increased to High. 04/04/23: Position has improved. Funding for next 7 months has been confirmed and approach approved by PAB so green light to continue. Decision on future years funding dependent on the business case to be presented at the Oct Investment Committee. Potential ramifications of AHDB decision need to be assessed. 02/05/23: Outstanding funding and/or sponsorship decisions could have reputational impacts. The target date was moved out to align with a major IC meeting in October which will inform future funding and assumes sponsorship has been resolved.
R011 |  | Fraud | 2022-10-10 | StuartMcDonagh/Simon Freeman | StuartMcDonagh/Simon Freeman | Open | Technology | Defra | If LI systems are subverted or fraudulent entries accepted. | Because of an absence of adequate mitigating controls, documentation and testing. Or SLT have decided to accept the risk (low likelihhod) | Then the quality and traceability of livestock may be compromised, increasing the likelihood of chronic endemic livestock diseases becoming prevalent, and reducing consumer confidence in the provenance of British meat and livestock products. | Fraud event | Med | High | Medium | Severe | Slow | Cautious | Transfer | 1) Engaging with James Couzens in Defra Food Security (Sector Cyber Strategy Lead Defra, and NCSC). 2) Putting in place a Fraud Strategy covering both fraud risk within LI and industry fraud. | High | Low | Moderate | 1 | 2024-03-31 |  | 193 | No | 10/10/2022: Raised in RSM Fraud and Bribery Risk Assessment July 2022 as FBR0 05/09/2022: MW comment: Usually, to own a risk, you have to be able to mitigate the risk, or close the risk completely. LI do not own enforcement and inspection, nor the policy decisions which would lead to the removal of paper. So I think there is a choice for the MD - accept and acknowledge the risk as you have stated, but in our corporate risk register, this would be escalated to be transferred to the other parts of the Defra group to own the mitigating actions, or choose not to accept this as a stated risk in the first place. 27/07/2022: RSM comment: We felt it would be useful to have a risk of this type to cover that LI have considered this as a fraud risk, but do not know enough about the controls/assurances you have in this area to be able to score it. It may be that Defra already have a risk of this nature, and are they are the owners of the data, whereas LI is the processor so have no control over the risk. 29/11/22: Specific fraud of not building a system that can be perverted by livestock industry into supporting or committing fraud within the livestock industry. 09/01/23: Actively chasing down flaws in the model. Concept of ownership being included in design to help reduce fraud. 07/02/23: To be raised at ARAC and take their advice on any further risk reduction actions. 07/03/23: No change. Covered by Fraud Strategy. 04/04/23: ARAC on 20th April to see if they have any concerns or recommendations. 02/05/23: Fraud in two parts, within the industry that LI may or may not enable or spot and the corporate aspect that LI is working on as a design principle. Ongoing risk is being actively managed and monitored.
R012 |  | Temporary staffing | 2022-10-20 | Stuart McDonagh | Wayne Augur | Open | People |  | IF inappropriate payments are made to staffing agencies, | Because of an absence of adequate mitigating controls, documentation and testing. | THEN value for public money will not be achieved. |  | Low | Low | Low | Moderate | Slow | Averse | Treat | No gaps in control identified | Low | Low | Moderate | 1 | 2023-03-31 |  |  |  | 21/11/2022: Timesheets / Activity Reports to be approved by hiring manager as a pre-requisite for invoice payment. 13/12/2022. No change. 20/12/2022. No change. 05/01/2023. No change. 07/02/023: Next Alpine review of costs and margins on 07/03/23 21/02/23: No change.
R013 |  | Working elsewhere on Company time | 2022-10-20 | Stuart McDonagh | Zoe Hodgkinson | Open | People |  | IF an employee works for another employer on LI Ltd time, by reporting sick when they are actually fit for work, or otherwise, | No formal process to obtain declarations of interest, incl secondary employment, after appointment, although it is an ongoing requirement in staff contracts. | THEN productivity will be lost and there may be a failure to achieve other corporate objectives., and may incur additional cost to cover those duties. |  | Low | Low | Medium | Moderate |  | Open | Treat | Implement Declaration of Interest policy? | Low | Medium | Moderate | 1
R014 |  | FBR5: Declarations of interest | 2022-10-20 | Stuart McDonagh | Zoe Hodgkinson | Closed | People |  | IF staff fail to properly manage conflicting interests, | Because No conflicts of interest policy No formal procedure to capture interests/nil returns No process to review/manage declarations No LI Ltd register of interests | THEN these may be exploited for personal gain resulting in failure to achieve value for public money and giving rise to an impression of impropriety amongst members of the public. |  | Low | Medium | High | Severe |  | Open | Treat | Implement Declaration of Interest policy? Implement CoI process? | Medium | High | Severe | 2 |  |  |  |  | 138-140 and 142-148 are subsidiary to 135
R015 |  | Mandate fraud | 2022-10-20 | Stuart McDonagh | Jackie James/AHDB | Open | Financial |  | IF unauthorised bank accounts are set up or unauthorised amendments are made, | Processes followed by AHDB have not been shared so a detailed review has not been possible. Potential areas for consideration are: – Cyber-attacks leading to email account compromise, and strength of IT controls in place at AHDB. – Failure to set up two factor authentication for email account access on new device or for password change. | THEN monies could be diverted to criminals instead of being paid to genuine supplier accounts. |  | Med | Medium | High | Severe |  | Averse | Treat |  | Medium | High | Severe | 2 |  |  |  |  | 138-140 and 142-148 are subsidiary to 135
R016 |  | Ghost employees | 2022-10-20 | Stuart McDonagh | Jackie James/AHDB | Open | Financial |  | IF ghost employees or duplicate payments are added to pay runs, | Because of an absence of adequate mitigating controls, documentation and testing. Or SLT have decided to accept the risk (low likelihhod) | THEN fraudulent payments may be made. |  | Med | Low | Low | Moderate |  | Averse | Tolerate | NA | Low | Low | Moderate | 1 |  |  |  |  | 138-140 and 142-148 are subsidiary to 135
R017 |  | FBR9: Changes | 2022-10-20 | Stuart McDonagh | Jackie James/AHDB | Closed | Financial |  | IF grading for an employee is changed fraudulently, | Because of an absence of adequate mitigating controls, documentation and testing. Or SLT have decided to accept the risk (low likelihhod) | THEN an employee could receive additional income they are not entitled to and value for public money will not be achieved. |  | Med | Low | Low | Moderate |  | Averse | Tolerate | NA | Low | Low | Moderate | 1 |  |  |  |  | 138-140 and 142-148 are subsidiary to 135
R018 |  | Leavers | 2022-10-20 | Stuart McDonagh | Jackie James/AHDB | Open | Financial |  | IF former employees remain on the payroll and continue to receive payment, | Because of an absence of adequate mitigating controls, documentation and testing. Or SLT have decided to accept the risk (low likelihhod) | THEN an employee could receive additional income they are not entitled to and value for public money will not be achieved. |  | Med | Low | Low | Moderate |  | Averse | Tolerate | NA | Low | Low | Moderate | 1 |  |  |  |  | 138-140 and 142-148 are subsidiary to 135
R019 |  | Expenses | 2022-10-20 | Stuart McDonagh | Jackie James/AHDB | Open | Financial |  | IF fictitious or false claims are submitted by employees and paid, | Because of an absence of adequate mitigating controls, documentation and testing. Or SLT have decided to accept the risk (low likelihhod) | THEN an employee could receive additional funds they are not entitled to and value for public money will not be achieved. |  | Med | Low | Low | Moderate |  | Averse | Tolerate | NA | Low | Low | Moderate | 1 |  |  |  |  | 138-140 and 142-148 are subsidiary to 135
R020 |  | Invoice fraud | 2022-10-20 | Stuart McDonagh | Jackie James/AHDB | Open | Financial |  | IF duplicate, inflated, inaccurate or fake invoices are paid, | Failure to have a COI process in place may result in inadequate segregation of duties for invoice authorisation. | THEN this can result in failure to achieve value for money or direct loss of public funds. |  | Med | Low | Medium | Moderate |  | Averse | Treat | Implement CoI process? | Low | Medium | Moderate | 1 |  |  |  |  | 138-140 and 142-148 are subsidiary to 135
R021 |  | Direct debit or bank transfers | 2022-10-20 | Stuart McDonagh | Jackie James/AHDB | Open | Financial |  | IF unsuitable individuals gain access to account information, | Because of an absence of adequate mitigating controls, documentation and testing. Or SLT have decided to accept the risk (low likelihhod) | THEN unauthorised transfers or spends may be made from LI Ltd bank accounts via the setting up of direct debits. |  | Med | Low | Medium | Moderate |  | Averse | Tolerate | No gaps identified | Low | Medium | Moderate | 1 |  |  |  |  | 138-140 and 142-148 are subsidiary to 135
R022 |  | Procurement | 2022-10-20 | Stuart McDonagh | Karen Dobson | Open | Commercial |  | IF LI Ltd fails to control and manage procurement processes, | No formal or established policy around single tender waivers No formal COI process currently in place for procurements Lack of internal procedures to cover management of full contract lifecycle | THEN these may be manipulated or subverted by internal actors or by external collusion, enabling the creation of ghost suppliers or contracting with unsuitable suppliers, resulting in direct fraud losses or failure to achieve best value for public funds. |  | Med | Low | Medium | Moderate |  | Averse | Treat | Implement Single Tender Waiver Policy | Medium | Medium | Moderate | 1 | 2023-05-31 |  |  |  | 29/11/22. Draft singtle tender process issued for comments 13/12/22. Comments received to be considered and final version of process baselined - WIP. 20/12/22: No change. Previous action c/f. 05/01/23: No change. Previous action c/f. 11/01/23: "Likelihood" reviewed and changed to Low 07/02/23: STA policy v0.2 issued for comment 6/2. Aim to baseline by 13/2 21/02/23: STA policy baselined 20/2 02/05/23: Single Tender Policy is in place. KD to provide an update and store the Defra STA template. | Document COI process | Wayne Augur | Closed |  | 2022-11-04 |  | Document Single Tender process | Wayne Augur | Closed | 2 | 2022-11-30
R023 |  | Lack of effective contract and supplier management | 2022-11-08 | Stuart McDonagh | Karen Dobson | Open | Commercial |  | If LI fails to effectively manage contract deliverables, LI obligations, and supplier obligations as set out in contractual agreements | Because of the lack/loss of commercial expertise in the organisation and/or a lack of Contract Management processes. | Then i) Value realisation under the contractual agreements may not be achieved resulting in poor performance and/or poor value for money; ii) Wider delivery objectives may not be met; iii) Compliance issues may arise where contract values or durations are greater than originally stipulated; iv) Risk of fraudulent activity increases; v) LI may be forced to extend incumbent arrangements or award new contracts on a Direct Award basis which may give rise to an increase in current prices or introduction of new terms which may be difficult to successfully mitigate or avoid. |  | HIgh | Medium | Very High | Critical | Medium | Cautious | Treat | 1. Contract management processes to be developed based on CCS 'Bronze' 'Silver' and 'Gold' tiering levels; 2. Contract register to be regularly updated to include a review of contract end dates and trigger dates for review; 3. Commercial pipeline to be developed (and updated as necessary subject to outputs from the strategic review) which links expiry of contracts with plans to procure and implement replacement arrangements; 4.Livestock Transformation Programme Board to begin planning now for funding arrangements and spend controls approval for future years. 5.Contracts requiring extension/renewal beyond FY22/23 to be flagged to SRO by LI MD with a recommendation to extend or replace based on current knowledge of delivery landscape. | Medium | Medium | Moderate | 1 | 2023-05-31 |  | -112 | Yes | 08/11/22 Replaces risks LI-130 and LI-131 Contract Mgt Process v0.2, Obligations Management Process v0.1 and Sample Obligations Tracker documented. Draft Commercial Pipeline v0.4 and Pipeline POAP v0.5 under active review Initial view of expiring contracts prepared and included in Pipeline POAP v0.5 in readiness for LI MD discussions with SRO 13/12/22. Pipeline status now included as part of monthly Commercial dashboard. 20/12/22: No change. 05/01/23: No change. 09/01/22: Using the new Sheep contract to bed in obligations management. In discussion with TCS about how LI do that through either monthly service review meetings or in separate commercial meetings. Once the model for TCS is agreed we can start rolling it out on subsequent new contracts. 07/02/23: All actions closed. Obligations tracking live via weekly Transition Boards 21/02/23: No change 07/03/23: Wayne Augur has handed in notice. Replacement plan in progress. Testing procurement in progress and suggest taking the opportunity to use Cadance service contract as a stop gap handover from Wayne. Residual L increased to Medium. 04/04/23: KD to action 02/05/23: KD has started contract management activities with key strategic contracts. | Document approach to contract management | Wayne Augur | Closed |  | 2022-08-31 | Yes | Finalise commercial pipeline (to include outline sourcing model) | Wayne Augur | Closed | 1 | 2022-11-30 | Yes | Contracts requiring extension/renewal beyond FY22/23 to be flagged to Paul Caldwell (SRO) by LI MD with a recommendation to extend or replace | Ian Hewett | Closed | 2 | 2022-11-30 | Yes
R024 |  | Lack of funding or support for run and maintain activities | 2022-11-08 | Ian Hewett | Ian Hewett | Open | Governance | Defra | If LI is not provided adequate funding then progress on a fully effective multi-species service will stall. | Because the LI structure is no longer appropriate or the funding for future of LI is not available | LI no longer becomes viable, the service will either cease or need to be transferred (novated) to another organisation resulting in significant delays. If no funding is provided or funding levels are too low then a fully effective multi-species service will be delayed and over a longer period resulting in delays to the benefits realisation. | Funding decision | High | High | Very High | Critical | Slow | Cautious | Treat | 1) LITP secured 7 months funding to the end of September 2023 2) Confirmation that LI run and maintain cost is included in the annual business planning cycle. | High | High | Critical | 3 | 2023-10-31 |  | 41 | No | 09/01/22: IH in discussions and will escalate to LTPB. Risk will deteriorate if we do not get timely response. Inherent likelihood increased to HIGH. FBC will not be ready for a March Investment Committee, the transformation programme realise that whilst LI is at FBC stage, remaining transformation programme projects are not. SF has proposed submitting a business case for the transformation programme of which LI is the first FBC underneath it and buy themselves the funding and time to complete the remaining work otherwise we will not get to March/April IC. 07/02/23: LI have contributed a lot of work towards a FBCbut limited response from wider Defra groupand a lack of clarity on when Defra will able to complete the FBC with a timeline of 1st April. Residual L and I increased to High. Highlight in Board Report. 07/03/23: No change 13/03/23: The FBC is now expected to be submitted to the Defra IC in October 2023. A funding request for the next 7 months is being submitted to the March IC. Target date needs amending. 04/04/23: Paul McGuiness has suggested a June commission. IH to update SK. Spectre of a retrospective among some members of IC. 02/05/23: Confirmation that LI run and maintain cost is included in the annual business planning cycle. Beholden to Investment Committee for funding of future development beyond October 2023. Risk to be split in two parts, BAU and Programme
R025 |  | Scoteid review may delay the current roadmap of delivery | 2022-11-16 | Simon Freeman | Simon Freeman | Closed | Technology | Paul Caldwell (LTPB) | The Defra Livestock Information Transformation Programme Board (LTPB) has requested a review of the suitability of ScotEID as a potential solution for LI to build the next phase of multi-species and cattle. The proposal is to have DDTS undertake the review. | Scoteid was considered previously before the CLA solution was procured and ScotEID was not taken forward. Wales adopted ScotEID temporarily to deliver sheep and then abandoned the solution for multi-species and cattle functions due to a number of reasons to do with the way ScotEID has been built. The consideration of a way forward for LI has resulted in a revisiting of the scoteid solution as a way forward. | There are a number of impacts. Firstly, the review itself will take time and it is unclear whether progress can be made in LI until that option is considered. Should LI be asked to wait for an outcome, the current plans and spend forecasts will no longer be valid and new ones will be need post review should the outcome be to move to Scoteid. The second impact is linked to the outcome. Should DDTS determine that ScotEID is the solution, LI will have a technical solution imposed upon it that it will not have done any due diligence on. Furthermore, the accountability for the solution would need to sit with DDTS rather than LI until a time when LI could undertake its own due diligence on the solution. Should SCoteid be put as the future solution, a full impact assessment would be needed to ascertain the gap between current functionality (the scottish solution) and the future processes and policies in England that would need to be implemented. A full assessment by LI could take 3 to 6 months before any plans or costs could be committed to. This will result in significant delays to the cattle implementation and it would be unclear whether budgets could be forecast ahead of the Q4 22/23 period when investment for future years would be decided. |  | High | High | High | Critical | Fast | Cautious | Treat | 1) The proposal is to limit the ScotEID review to a brief technical consideration based upon the Welsh feedback that it is not a suitable platform upon which to build. 2) Having Wales already discounted the solution, the review should consider the ratification of the Welsh view (on the ScotEID technology) rather than a full stand alone review. | Low | Very High | Severe | 2 | 2023-04-30 | 2023-05-02 | -143 | Yes | 09/01/23: The review has recently kicked off. Initial discussions suggest there is very little risk that the review will not support the current solution/plan. 26/01/23: The review has completed but not reported. Initial discussions suggest there is very little risk that the review will not support the current solution/plan. 07/02/23: Whilst the independant review has concluded there is still resistance in Defra. IH to take offline with SF. 07/03/23: Residual L reduced to medium. Residual I increased to V High (given that LI will have signed off HLD). Rating aligns with LI-R132 04/04/23: Residual likelihood reduced to Low 02/05/23: It was agreed at the LITP Board meeting of 26th April that SCOTEID will not be taken forward. Risk Closed.
R026 |  | Head of Finance departure and lack of Finance Director | 24/11/22 | Ian Hewett | Zoe Hodgkinson | Closed | People | LI Board | If the HoF leaves and LI does not have a Finance Director | Because the HoF finds another role and/or the ownership partners are slow to authorise a replacement Finance Director | Then LI is without adequate financial goverance and control that increases the risks of compliance failure, of fraudulent activity, failure to meet obligations under company law. Creates risk to overall control and delivery environment. |  | High | High | Very High | Critical | Fast | Cautious | Treat | Recruitment of Finance Director and adequate succession planning. | Medium | Medium | Moderate | 2 | 2023-01-31 |  | -232 | Yes | 08/12/22: This is either an Issue or a closed risk. CHi is leaving and a recruitment has opened for an FD. If there is a risk it is the gap between Chi leaving and FD starting, which I am seeking to mitigate by securing a temporary replacement for Chi.
R027 |  | Delays to legislative changes | 2022-11-29 | Ian Hewett | Simon Freeman | Closed | Technology | Paul Caldwell (LTPB) | The requirement to change legislation to alter industry behaviours delays delivery of the multi-species data service |  |  |  |  | High | Very High | Critical |  |  |  |  | Medium | High | Severe | 3 | 2023-03-31 |  | -173 | Yes | 8/12/22: Closed because duplicationof 155
R028 |  | Regulation changes delay the live deployment dates | 2022-01-12 | Simon Freeman | Simon Freeman | Open | Delivery | Paul Caldwell (LTPB) | The time it will take to change and implement legislation that supports movements and traceability could cause delays to the live dates of the new solutions | Timelines for changing legislation, policy discussions, consultation and parliamentary time create a long burn rate for changes | Delays to legislation would mean key transformations such as BEID and passport removals cannot be implemented ahead of predicted legislation March 25. This will mean we either implement passports and go live in MVP or have to not include the cost of implementing passports and delay any go live (MVP) beyind March 25 |  | Med | High | High | Critical | Fast | Cautious | Treat | Work with policy to identify ways to go live early through bringing forward legislation or enable early go live with legislation to follow. | Medium | High | Severe | 2 | 2023-10-31 |  | 41 | No | 09/01/23: Initial schedule does not extend beyond BEID. 07/02/23: Residual L increased to High 07/03/23: No change 04/04/23: No change. Will not be resolved by end of April but will force us to review. 02/05/23: Policy is planning regulatory changes by 2024 but this is less important because of the passport decision. Residual Likelihood reduced to Medium.
R029 |  | RPA customer service centre industrial action | 2022-06-12 | Stuart McDonagh | Paul Hitchenes/Paul Wills | Closed | Operations |  | If strike action in the customer service centre proceeds it will have a significant impact on RPA operations ability to administer the work of the RPA at a critical time of year. | PCS members in the customer service centre to take strike action on 13, 14, 15, 16, 19, 20, 21, 22, 23 December 2022 and 3, 4, 5, 6, 9, 10, 11, 12, 13 January 2023, and 1st February. | Could impact LUIS (SM) and CTS (SF) and delay handover of bureau service | Strike action | Med | Low | High | Moderate | Fast | Minimal | Tolerate | 1) According to BCMS any proposed strike won't impact cattle go-live or the LUIS service. 2) LI have almost completed UAT, and model office / training happen after the strike ends. 3) Most project work is paused during the Christmas break. | Very Low | Very Low | Low | 1 | 2023-04-30 | 2023-05-02 | -143 | Yes | 13/12/22: Tim Philips; According to Paul Moody it won't impact cattle go-live or the LUIS service, so I think its low risk at the moment. We have almost completed UAT, and model office / training happen after the strike ends so I think we will be okay. Most project work is paused during the Christmas break so I am not anticipating any issues. 09/01/23: Unease across the Public Sector and more action to come. 07/02/23: Current strike action finished on 1st Feb with no impact on the LUIS service. Residual I reduced to Low. 07/03/23: Strikes have passed with no noticeable impact and LUIS cattle has now gone live. Residuals reduced to Very Low but risk remains under review. 04/04/23: No longer a risk to RPA or LI service. Keep open for a month with a recommendation to close if there is no change at May review. 02/05/23: No further action planned and previous action has not impacted LI to any significant degree. Risk Closed
R030 |  | Procurement resourcing bottleneck | 2022-12-12 | Karen Dobson | Karen Dobson | Open | Commercial |  | Insufficient commercial capacity to deliver and manage required commercial arrangemnents in the short term | Commercial pipeline reflects pent up demand that has been placed on hold pending outcomes and instructions following the strategic review together with lack of confirmed future year funding. | Dependency on commercial activity may be a blocker for timely programme delivery and progressing corporate objectives if commercial arrangements cannot be put in place when needed. | Delivery delays | High | Medium | Medium | Moderate | Fast | Minimal | Treat | 1) 'Procurement as a Service' contract in place with Cadence Innova would enable extra commercial capacity to be used on a project-by-project basis; 2) Review planning and sequencing of commercial pipeline activities to ensure priorities align to outline programme delilvery plans and corporate commitments. | Medium | High | Severe | 2 | 2023-05-31 |  | -112 | Yes | 13/12/22. Focussed execution against commercial pipeline continues with 11 of the 23 commercial projects either completed or in-flight. 20/12/22: Meeting to discuss programme priorities scheduled for 20/12/22 05/01/23: Meetings held. Pipeline plan to be refreshed. 09/01/23: No change 07/02/23: Re-sequencing of commercial pipeline complete. Revised Target Mitigation Date is a monitor and review date with a view to closure. 21/02/23: No change. 07/03/23: Gap in time recruiting a replacement for Wayne increases the Residual L increased to High. 04/04/23: KD to review and update. 02/05/23: Process in place to get additional commercial support (interim and permanent) to mitigate risk. Residual Likelihood was reduced to Medium, Residual Impact increased to High. | Set up planning meetings to ensure prioritisation aligns to outline programme delivery plans | Wayne Augur | Closed |  | 2022-12-31 | Yes
R031 |  | risual struggling to deliver contracted services | 2023-02-07 | Stuart McDonagh | Paul Wills | Closed | Operations |  | risual struggling to deliver contracted services. Not recorded in ADO. | risual do not have the internal capabilities, practices, repeatable processes, and competencies for the services contracted. | Impeding maturity of LI service, slow to implement new enhancements, delays to DR testing and documented incident response plans. Maturity of SOC and cyber response. |  |  | Very High | High | Critical | Fast | Eager | Treat | Strategic direction and LI Future Mode of Operation (FMO). 1. Insource Service Desk and Service Management Practices (Paul H leading) 2.Procure IT Operations / Azure Platform to align to riusal contract end point 14/11/23 (Paul W leading) 2.Procure SOC as a Service and Cyber Incident Response specialism to align to riusal contract end point 14/11/23 (Paul W leading) | Low | Medium | Moderate | 1 | 2023-11-14 | 2023-05-02 | 55 | No | 07/02/23: Advocating a move away from risual based on poor performance. Triggered service team to work through remedial actions. Its an interim contract that’s up for expiry so LI needs to review sourcing options and recomplete (regardless of performance). At some point it should be moved to Issue register with remedial action in progress. 07/03/23: Improvement plan and work on new tender in progress. 04/04/23: No change. Continue to drive risual performance and prepare for new partner procurement. 02/05/23: Managing commercial and operational mitigations pending the re-procurement. Given non-performance and a future strategy that requires an alternative structure mean this is to be transferred to the Issue Register I084.
R032 |  | Risk from third party software issues | 2023-02-07 | Stuart McDonagh | [16 empty] | Low | Low | Moderate | 1 |  |  |  |  | 07/03/23: Potential reputational damage
R033 |  | Cross Compliance | 2023-02-20 | Simon Freeman | Simon Freeman | Open | Delivery | Defra | Data quality will reduce as cross compliance ends | Cross compliance ending will result in no direct fiancial impact on the keepers for non compliance as subsidies will no longer be tied to compliance | Data quality may drop as incentive to comply with livestock data provision (registration, movements etc) diminishes |  |  | Very High | Medium | Critical | Medium | Eager | Transfer | The risk is created from changes to policy resulting in potential adverse conditions for LI to generate good quality data for traceability. Defra need to review the policy and suggest alternatives to cross compliance to incentivise the keepers to comply | High | Medium | Severe | 2 | 2024-03-31 |  | 193 | No | 20/02/23: Escalated risk to LITP PD for consideration. 07/03/23: No change 04/04/23: EU cross compliance subsidy requirement comes to an end in 2024. It will be replaced by Civil Sanctions. Need to assess implications, if any, for LI. 02/05/23: Escalated to LITP.
R034 |  | Investment Committee does not provide funding for future development | 2023-05-02 | Ian Hewett | Ian Hewett | Open | Governance | Defra | If LI is not provided adequate funding for future development then progress on delivery of a multi-species service for livestock traceability will stall. | Because the LI delivery structure is no longer deemed appropriate or the funding for future development of the platform and service is not available | LI no longer becomes viable, the programme will either cease or need to be transferred (novated) to another organisation resulting in significant delays. If no funding is provided or funding levels are too low then delivery of a fully effective multi-species service will be delayed and over a longer period resulting in delays to the benefits realisation. | Investment Committee decision | High | High | Very High | Critical | Slow | Cautious | Treat | 1) LITP secured 7 months funding to the end of September 2023 whilst a business case is prepared for the Defra Investment Committee (IC). 2) Programme Director has proposed submitting a business case for the LITP transformation programme of which LI is the first FBC underneath to secure future funding. 3) The FBC is expected to be submitted to the Defra IC in October 2023. | High | High | Critical | 3 | 2023-10-31 |  | 41 | No | 02/05/23: Confirmation that LI run and maintain cost is included in the annual business planning cycle. Beholden to Investment Committee for funding of future development. Risk to be split in two parts, BAU and Programme
Change of political administration.
Formulas:
Days until target date = IF(Risks[[#This Row],[Target Mitigation Date]]="","",Risks[[#This Row],[Target Mitigation Date]]-TODAY())
Overdue?2 = IF(ISBLANK(Risks[[#This Row],[Target completion date]]),"",IF(Risks[[#This Row],[Target completion date]]<TODAY(),"Yes","No"))
Overdue?27 = IF(ISBLANK(Risks[[#This Row],[Target completion date6]]),"",IF(Risks[[#This Row],[Target completion date6]]<TODAY(),"Yes","No"))
Overdue?28 = IF(ISBLANK(Risks[[#This Row],[Target completion date7]]),"",IF(Risks[[#This Row],[Target completion date7]]<TODAY(),"Yes","No"))
Note on C8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I agree we should have this risk, but it feels confused. Should we have owners outside of the company? I agree the risk needs escalation to the LTPB. Moreover, Paul doesn't sit on the ADPG Traceability group. Reply: Simon Freeman has reworded this risk and become the risk owner
Note on L9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Needs an update Cattle Sprint 0 is complete. The delay is in next steps - bEID, Digital Passports and Automated Moves. Reply: Impact description has been updated
Note on C10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Risk reworded to reflect it as a perm risk
Note on O10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should the likelihood be higher?
Note on C16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AHDB added
Note on C32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is either an Issue or a closed risk. CHi is leaving and a recruitment has opened for an FD. If there is a risk it is the gap between Chi leaving and FD starting, which I am seeking to mitigate by securing a temporary replacement for Chi. Reply: Closed
Note on C33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Close, as per my email to Ian D Reply: closed

## Issues
Unique Issue ID (should be the functional area/project's unique 2 or 3 digit suffix, followed by 'I' for 'issue', followed by a unique consecutive number beginning 001 - i.e. LI-I001) | ADO ref for items escalated through project or programme owners | Defines the short name for the issue. Must be a short title by which the issue can be easily recognised and referred, whilst providing some context as to what the risk actually is. | The date this issue has been identified. | The person identified to own and monitor the risk. This person is responsible for verifying that the issue is managed and tracked appropriately through its lifecycle | The person identified with overall responsibiliy for this area of activity. The person to perform an evaluation of the issue. | Specifies the progress of the issue | Displays the category to which the issues belongs. | Specifies who the issue has been escalated too | Description of the issue with sufficient information for one to understand the matter. It should be written clearly, outlining the cause and effect of the issue. | Detailed impact description of the issue on the project objectives, including who would be affected and how. | High-level assessment of the financial (including commercial) impact, for example increased cost of delay, Low, Medium or High | Defines the effect of the issue on the project / programme objectives after mitigating actions have been taken: Low, Medium, High or Very High | Defines priority level for the issue: Low, Medium, High or Very High | Combined Impact/Priority Calculation is automatic | Assessment of the progress against mitigating/resolving the issue. On target (1), caution (2) or not on target (3) | Defines issue response plan to resolve the issue. It should capture the types of actions required to manage the issue. | The approach to managing issues should be specified as one of the following: Treat (management/mitigation actions);Terminate (stop the activity causing the issue); Transfer (pass the issue to a third party); Tolerate (accept the issue without management actions) | Defines the date the issue is targeted to be resolved. | Defines the actual date the issue is resolved. | Days until the Issue target resolution date (calculated) | Is the Issue overdue? (calculated) | Updates on any change of status and the reason. It should highlight recently completed activities to transfer, mitigate or resolve the issue. | Defines the short name for the action that is listed in the resolution/mitigation strategy. | Defines the resource responsible for verifying that the action is managed and tracked appropriately through its lifecycle | Specifies the progress of the Action | Assessment of the progress completing the action. On target (1), caution (2) or not on target (3) | Defines the date the action is targeted to be completed. | Is the Action already overdue? (Calculated) | Defines the short name for the action that is listed in the resolution/mitigation strategy. | Defines the resource responsible for verifying that the action is managed and tracked appropriately through its lifecycle | Specifies the progress of the Action | Assessment of the progress completing the action. On target (1), caution (2) or not on target (3) | Defines the date the action is targeted to be completed. | Is the Action already overdue? (Calculated) | Defines the short name for the action that is listed in the resolution/mitigation strategy. | Defines the resource responsible for verifying that the action is managed and tracked appropriately through its lifecycle | Specifies the progress of the Action | Assessment of the progress completing the action. On target (1), caution (2) or not on target (3) | Defines the date the action is targeted to be completed. | Is the Action already overdue? (Calculated)
[23 empty] | Action 1 | [5 empty] | Action 2 | [5 empty] | Action 3
Issue ID | ADO | Issue Name | Date identified | Owner | Domain Owner | Status | Issue Domain Category | Escalation | Description | Impact Description | Financial Impact | Impact (I) | Priority | Issue Rating | Issue RAG | Resolution Plan | Response Type | Target Resolution Date | Actual Resolution Date | Days until due date | Overdue? | Latest Update | Action Name 1 | Owner2 | Status2 | Action RAG | Target completion date | Overdue?2 | Action Name 2 12 | Owner 13 | Status24 | Action RAG5 | Target completion date6 | Overdue?27 | Action Name 3 | Owner 14 | Status25 | Action RAG6 | Target completion date7 | Overdue?28
LI-I071 |  | Customer requirements are incomplete | 2022-02-01 | Defra | Simon Freeman | Closed | Technology | Paul Caldwell (LTPB) | No agreed customer requirement for cattle that maps from outcomes through risks and needs, encompassing regulatory and business process requirements. | Inadequate decision-making landscape for solution design. LI Ltd is unable to measure service and programme delivery progress against the requirement. |  | Very High | Very High | Critical | 3 | LI Ltd to continue to set out what it requires from Members of the Company to inform cattle sprint 0. Work proactively with colleagues to help shape/inform the requirement as required. If necessary, slow down delivery if the requirement is not sufficiently clear, setting out the consequences of doing so. | Transfer | 2022-03-15 | 2022-01-11 | -554 | Yes | 01/11/22: Not aware of any significant missing gaps in cattle requirements that would prevent us from getting on with the multi-species cattle build. Action SF: To be reworded as a Risk. | Set out what is needed from members of Company to inform cattle sprint 0. | Simon Freeman | Closed |  |  |  | Work to help shape/inform the requirement as required | Simon Freeman | Closed |  |  |  | If necessary, slow down delivery if the requirement is not sufficiently clear, setting out the consequences of doing so. | Simon Freeman | Closed
LI-I073 |  | Member direction and involvement | 2022-02-22 | AHDB/Defra | Ian Hewett | Open | Governance | AHDB | LI Ltd does not have stable board membership from company Members on its Board. LI Ltd does not have the authority to ensure that the board is equipped with the skills required to ensure effective company oversight. | Regular changes weaken relationships and trust and reduce the understanding of company mission, structure and associated rationale. Weakens LI Ltd.'s overall influence and ability to drive collaborative delivery. | Low | High | Medium | Severe | 2 | 1) The UK CVO has become the Defra member on the Board. 2) An FD has been recruited and is the sixth Board member (from the seven Board positions). 3) Invest in relationships through Defra Livestock Transformation Programme Board LTPB. 4) Clarify Defra input into the LI Board and associated governance. 5) Self assessment evaluation conducted and findings reviewed with the Chair. 6) Defra and AHDB sponsors are currently considering changes to sponsorship of the company, with the expectation that Defra becomes the major shareholder. Once confirmed the sponsorship changes are expected to result in changes to the Board and Audit and Risk Committee. | Transfer | 2023-06-30 |  | -82 | Yes | 01/11/22: Recruitment of 2 vacant posts on the Board is dependent on pending approval by AHDB (as per the GOM). Industry NED and Finance Director. 29/11/22: Moving towards more stable Board. Evaluation Assessment likely to highlight other issues. Associated risk closed LI-R133 08/12/22: New mitigation. I have opened a recruitment for an FD, which will be the sixth Board member. 09/01/23: Industry Rep discussed at Dec TDUG. 07/02/23: Still waiting for T&F group to report to LTPB (22 Feb) that will lead into wider governance piece. 07/03/23: IH has reviewed all the open actions from the T&F group and intends to provide a response linked to LI position on KPIs. Decisions will be taken at sponsorship meetings due to meet before the end of March which has resulted in the LI Board meeting being delayed until 6th April. 04/04/23: Clarity emerging with AHDB decision awaiting confirmation. 02/05/23: Resolution Plan updated. The expectation is that Board will get stronger as a result of these changes. Results of Self Assessment are to be discussed with Board Chair. | Invest in relationships through Defra Livestock Transformation Programme Board LTPB. | Ian Hewett | Closed | 2 | 2023-03-31 | Yes | Clarify Defra input into the LI Board and associated governance | Defra | Open | 2 | 2023-06-30 | Yes | Board and subcommittee makeup and purpose to be considered alongside Defra’s Strategic Outline Case (SOC) through a Defra convened task and finish group. | Defra | Closed | 2 | 2023-04-30 | Yes
LI-I074 |  | LI Ltd Governance | 2022-02-22 | AHDB/Defra | Ian Hewett | Open | Governance | SRO | Lack of clarity with regard to the role of the board and its delegations. Insufficient definition of LI governance structure within the Livestock Transformation Programme Board governance to provide clearly articulated roles, decision making, and delivery oversight functions. | Duplicative and conflicted governance creates overhead and distracts from delivery/decision making. Creates lack of clarity as to which decisions are within LI senior team delegations. Erodes trust and reduces confidence. Contributes to blame culture and poor job satisfaction | Med | High | High | Critical | 3 | 1) LI Ltd Board has requested a revised version of the GOM, highlighting areas needing clarification. 2) LI Ltd Board and subcommittees to be confirmed/redefined once Defra and AHDB have concluded proposed changes to the company's sponsorship. 3) LI Ltd MD to develop a decision making framework for consideration at the LTPB. | Transfer | 2023-06-30 |  | -82 | Yes | 1/11/22: Lack of progress from Task & Finish Group is becoming critical. Priority raised to High. 29/11/22: Target date updated to 31/3/23 08/12/22: T&F added to resolution plan 02/05/23: Resolution Plan updated. 09/01/23: Pending T&F outputs 07/02/23: Pending CVO response to Board Evaluation 07/03/23: Shendi Keshett now on Board as 6th Member. Potential that sponsorship decsions may require modification of the Board and its members. Situation has improved. 04/04/23: IH has started working on GOM, DA, and SSA
LI-I076 |  | LI Ltd Governance | 2022-06-14 | AHDB/Defra | Ian Hewett | Open | Governance | Paul Caldwell (LTPB) | The Governance Operating Manual and Delivery Agreement are now out of date because Members of the Company (AHDB/Defra) have changed the governance landscape. | Accountabilities, responsibilities and delegations for decision making between the LI Board, the LTPB and LI Ltd are not known or are out of date. Decisions could be taken without relevant authorisation or not taken at all. | Low | High | Medium | Severe | 2 | 1) Refreshing delegated authorities, accountabilities, and responsibilities of LI Ltd from AHDB/Defra in an updated GOM and Delivery Agreement following review of the company’s sponsorship model. 2) LI Ltd MD has produced and circulated a version of the GOM highlighting the areas for revision (e.g. AO and FD responsibilities). 3) LI Ltd MD to update the GOM based on the outcome of the Defra convened task and finish group that looks at sponsorship and corporate affairs to take forward recommendations of the Cabinet Office Review. | Transfer | 2023-06-30 |  | -82 | Yes | 1/11/22: Action: JD is to circulate the out-of-date GOM to Board members on receipt of the Accounting Officer confirmation letter. 29/11/22: Request from ARAC Chair to set aside those items of the GOM that are obsolete and put in place alternative arrangements. 08/12/22: T&F added to resolution plan 02/05/23: Resolution Plan updated. 09/01/23: Pending T&F outputs 07/02/23: No change. No point in updating the Delivery Agreement until sponsorship review is complete. Outside of LI gift. 07/03/23: No change. LI Board and T&F group aware that until sponsorship decisions have been made there is no need to update the GOM. When it is appropriate to update the GOM there will be an ambition in Defra to work with them to update the SSA (Statutory Services Agreement). 04/04/23: IH has started working on GOM, DA, and SSA | Obtain clarity of LI Ltd responsibilities from AHDB/Defra | LTPB | Open | 2 | 2023-06-30 | Yes | Refresh GOM and Delivery Agreement | Ian Hewett | Open | 2 | 2023-06-30 | Yes | 1/11/22: To circulate the out-of-date GOM to Board members on receipt of the Accounting Officer confirmation letter. | Jackie Darlow | Closed
LI-I077 |  | Loss of key individuals | 2022-06-30 | Ian Hewett | Stuart McDonagh | Closed | People | NA | Loss of Programme Director and COO | Negative inpact on operational running and delivery, time delays, and concerns over the efficacy of the procurement and the ability to successfully transition to replacement arrangements absent a Programme Director |  | Very High | Very High | Critical | 1 | Simon Freeman recruited and expected to join in early September as Programme Director. Recruitment of a replacement COO is underway | Treat | 2022-09-30 | 2022-10-10 | -355 | Yes | 06/10/22: Simon Freeman started as PD on 9 Sep. Stuart McDonagh starts as COO on 10 Oct | Recruit Programme Director | Ian Hewett | Closed | 1 | 2022-09-30 | Yes | Recruit COO | Ian Hewett | Closed | 1 | 2022-11-30 | Yes
LI-I078 |  | Lack of confirmed funding for subsequent fiscal years | 2022-04-08 | Vicky Moore | Colin Turner/Shendi Keshet | Open | Financial | SRO | Absence of medium and long term funding and/or SRO instruction to proceed. | LI will lose staff if we cannot forward commit beyond September 2023. The ability to pay staff (employees and contractors) is also at risk. | High | Medium | High | Severe | 2 | 1) Funding confirmation for BAU work has been confirmed by the LITP SRO. 2) A closure report for the sheep service was approved by Defra Investment Committee (7th Sep 22), providing financial authority for the remainder of the last financial year, and an expectation that LI Ltd will bid for BAU funding for future years. 3) The issue of contract termination notices for a suite of trigger points in September 2022 has been successfully mitigated. 4) Worsening situation on government financing. Leadership Team working on options and mitigating actions to counter a potential ask from the central government. Currently no commitment to future year funding for development beyond September 2023. | Transfer | 2023-06-30 |  | -82 | Yes | 01/11/22: Currently no commitment to future year funding for development. 29/11/22: Revised Business Case to go to October 23 Investment Committee. In the meantime LI have ambiguity of future funding particularly with regard to development. 08/12/22: The issue of contract termination notices for a suite of trigger points in September 2022 has been successfully mitigated. 07/02/23: Whilst an allocation exists LI cannot access the funding for development without an FBC. 07/03/23: Specifically relating to development work. A paper to be presented to the IC on 22nd March will only seek authority to draw down funds already allocated for next FY for development work. Run and maintain funds have been agreed for FY23/24 and FY24/25. Need IC to agree the recommendations in the paper before we can commit to supplier contracts beyond March. The three months committment agreed with SRO has evaporated. A six month agreement is being sought pending the buiness case being pepared by the Defra programme team with input from LI. Situation deteriorating. 04/04/23: Position has improved. Funding for the next 7 months has been confirmed and the approach approved by PAB so the green light to continue. Decision on future years' funding dependent on the business case to be presented at the Oct Investment Committee. Potential ramifications of the AHDB decision need to be assessed. Impact reduced to medium and priority reduced to high, overall severe. 02/05/23: Resolution Plan updated.
LI-I079 |  | Reputational Damage to LI Ltd and/or Defra | 2022-06-10 | Ian Hewett[/John Cross] | Ian Hewett | Closed | Governance | Paul Caldwell (LTPB) | Industry and wider stakeholder expectations regarding delivery of the multi-species service [platform] are not met because delivery does not proceed at pace or beyond the live sheep service. | Industry, suppliers, and staff loose confidence in the strategy, objectives and plans of LI Ltd. Industry support for LI Ltd and the intended outcome wanes. Suppliers disengage and key staff leave. |  | Very High | High | Critical | 2 | Secure future funding from Paul Caldwell/LTPB Secure go ahead for Cattle delivery from Paul Caldwell/LTPB | Treat |  | 2022-01-11 |  |  | 06/10/2022: Transferred from Risk following SLT RAID review 06/10/2022 - LI-R134 01/11/2022: Close issue and reopen (reword) LI-R134
LI-I080 |  | DA Data problem is being dealt with bottom up | 2022-08-11 | Simon Freeman | Simon Freeman | Closed | Data | Defra | While the data movements are covered by agreements, there is no clarity or strategy on how data across the DAs will be handled and will flow. This cannot be handled from the bottom up as is currently the case. | Complex inter organisation data flows causing data quality issues and high cost of maintenance | High | High | High | Critical | 3 | 1) LI to work with Defra on the DA problem from top down to agree a strategy on who will do what in the data area across Das 2) Aiming to simplyfy the requirements of disparate data sharing agreements (between different countries, organisations and species). One overarching agreement is not achieveable. Proposal to take papers to the DA for the LTPB seeking to align behind a single agreement for each of England, Scotland and Wales containing variance. Data alignment being led by Roger Goodwin within LITP. | Treat | 2023-04-30 | 2023-05-02 | -143 | Yes | 29/11/22: being worked on with design authority but a long way to go 09/01/23: Jill Moger starting to work on top down 07/02/23: Now sits with LITP, remains an issue to be tracked but not one LI can mitigate anymore 07/03/23: Aiming to simplyfy the requirements of disparate data sharing agreements (between different countries, organisations and species). One overarching agreement is not achieveable. Proposal to take papers to the DA for the LTPB seeking to align behind a single agreement for each of England, Scotland and Wales containing variance. Data alignment being led by Roger Goodwin within LITP. 04/04/23: Pending an update from SF/MD. LI had proposed to create something streamlined to cut down on the number of DSAs. That didn’t progress very far as an LI Ltd initiative and it was agreed something that couldn’t be achieved from the bottom up. Latest proposal is to transfer the streamlining of DSAs to LITP, while LI review DSAs where needed. 02/05/23: LITP has taken on the data issue through the Data Forum. To be tracked as part of Risk 89 going forward. Issue Closed.
LI-I081 |  | LIS Data Retention | 2023-01-09 | Malcolm Dunsmore | Simon Freeman | Open | Data | Defra | UK View Data Sharing Agreements with ScotEID and WG require data erasure. Review of DSAs in progress to add catlle to the exisitng Sheep, Goat and Deer agreements. The LIS has no process or procedure in place to manage data retention. Most other agreements are public task orientated with retention of data as long as is required. | Potential breach of agreements. DAs could decide to not share data if retention requirements are not met by the LIS. Data erasure could impact APHA reporting requirements/obligations. (Shows lack of holistic approach) | Medium | Medium | Medium | Severe | 2 | Addressed as part of LI-I081 providing a holistic understanding of data processing, including retention, across all organisations involved in livestock movement / disease traceability. Noting current guess, pre planning, is that Cattle data will be required for UK View c. end April 23. | Treat | 2023-07-31 |  | -51 | Yes | 06/01/23: matter discussed with Stuart/Simon. 07/02/23: Remains open until LI produce a basline set of documentation. Links to LI-R089. 07/03/23: See 07/03/23 comment for LI-I080 04/04/23: Update from MD. LI had proposed to create something streamlined to cut down on the number of DSAs. That didn’t progress very far as an LI Ltd initiative and it was agreed something that couldn’t be achieved from the bottom up. Latest proposal is to transfer the streamlining of DSAs to LITP, while LI review DSAs where needed. 02/05/23: Bipartite agreements and work to streamline are progressing.
LI-I082 |  | UK View DSAs with ScotEID and WG | 2023-01-09 | Malcolm Dunsmore | Simon Freeman | Open | Data |  | Engagement from ScotEID on UK View DSA for Cattle has gone cold, post questioning if a DSA was actually required. The DSA is based on personal data and the LIS does not get Scottish PD from ScotEID data but rather from AMLS2 (moving to SAM in the future). Engagement from WG is intermitent. | It may not be possible to include Cattle data in UK View without ScotEID and WG DSAs agreed to. | Low | High | High | Critical | 3 | Aiming to simplyfy the requirements of disparate data sharing agreements (between different countries, organisations and species). One overarching agreement is not achieveable. Proposal to take papers to the DA for the LTPB seeking to align behind a single agreement for each of England, Scotland and Wales containing variance. Data alignment being led by Roger Goodwin within LITP. | Treat | 2023-07-31 |  | -51 | Yes | 07/02/23: Remains open until LI produce a basline set of documentation. Links to LI-R089. 07/03/23: See 07/03/23 comment for LI-I080 04/04/23: Update from MD. LI had proposed to create something streamlined to cut down on the number of DSAs. That didn’t progress very far as an LI Ltd initiative and it was agreed something that couldn’t be achieved from the bottom up. Latest proposal is to transfer the streamlining of DSAs to LITP, while LI review DSAs where needed.
LI-I083 | 89508 | Newline software sending duplicate movements | 2023-02-02 | Graham Gosling | Stuart McDonagh | Closed | Operations |  | Issue 89508: Newline(market software) have had an issue where their software has been sending duplicated movements, this is causing down stream abattoirs/keepers problems as they have the same move many times. | Impact on Sheep Service | Low | Medium | Medium | Severe | 2 | 1) CLA team have produced an extract of the duplicates and we are working through this and cases that have been raised with Newline. 2) Newline so far have been able to undo the duplicated movements and this rectifies the problem 3) We should consider comms to the abattoirs to explain the problem as they will see this as a problem with our LI service. 4) GG will speak to Sarah O about how we tackle this on 31st Jan. 5) In the mean time we are consolidating the list of market moves and getting Newline to fix. | Treat | 2023-02-10 | 2023-03-07 | -222 | Yes | 07/02/23: Near to a third party resolution fix on 10/02/2023. Affecting performance. Impact and Priority reduced to Medium. 07/03/23: Issue closed
LI-I084 |  | risual struggling to deliver contracted services | 2023-05-02 | Stuart McDonagh | Paul Wills | Open | Operations |  | risual are struggling to deliver contracted services because they do not have the internal capabilities, practices, repeatable processes, and competencies for the services contracted. | Impeding maturity of LI service, slow to implement new enhancements, delays to DR testing and documented incident response plans. Maturity of SOC and cyber response. | Low | Low | Medium | Moderate | 1 | Managing commercial and operational mitigations pending the re-procurement. Strategic direction and LI Future Mode of Operation (FMO). 1. Insource Service Desk and Service Management Practices (Paul H leading) 2.Procure IT Operations / Azure Platform to align to riusal contract end point 14/11/23 (Paul W leading) 3.Procure SOC as a Service and Cyber Incident Response specialism to align to riusal contract end point 14/11/23 (Paul W leading) | Treat | 2023-11-14 |  | 55 | No | 02/05/23: risuals non-performance and a future strategy that requires re-procurement of alternative support structures mean Risk 158 has been transferred to the Issue Register
LI-I085 |  | Key permanent staff or any staff with specialist skill leave. | 2023-05-02 | Stuart McDonagh | Stuart McDonagh | Open | People |  | Key permanent staff or any staff with specialist skill leaving because losing key people is inevitable. They may take a new job opportunity, retire, suffer a long-term illness, or die unexpectedly. | A negative impact on operational running and delivery, cost overruns, time delays, and failed procurement due to a lack of resilience. |  | Very High | Very High | Critical | 3 | 1) Diversify LI Ltd’s approach to staff recruitment and retention. 2) Manage critical knowledge by documenting activities, identifying others for training and knowledge transfer and undertaking succession planning for key skills. 3) Create a great place to work, a supportive and inspired culture where delivery professionals feel empowered. 4) Undertake skills and services audit and establish the gaps. 5) Development of a new Target Operating Model including a Human Capital Management capability. 6) LI in process of creating baseline set of LI's own corporate HR policies, based on AHDB documentation by 31/03/23 7) Provide LI specific wording to fit into AHDB's templates for JD's 8) Tactically deploying PMO resources across the TOM pillars | Treat | 2023-06-30 |  | -82 | Yes | 02/05/23: Transferred from risk register R126
LI-I086 |  | Cash flow management | 2023-05-02 | Shendi Keshet | Shendi Keshet | Open | Financial |  | The inability of LI to generate invoices to Defra (in a format best suited to LI) in a timely fashion that enables LI to pay its suppliers in a timely fashion because of LIs reliance on AHDB. There is a very short time window after AHDB complete month end for LI to produce an invoice. This creates a single point of failure that can easily lead to delays. | LI is not in control of the timely payment of supplier invoices so any delay in AHDB process has a knock on effect and could delay payments to suppliers. |  | High | High | Critical | 3 | Dependency on AHDB until such time as the AHDB sponsorship change has been completed and LI can develop a new service offering that aligns with its business practices. | Treat | 2023-06-30 |  | -82 | Yes
Formulas:
Days until due date = IF(Issues[[#This Row],[Target Resolution Date]]="","",Issues[[#This Row],[Target Resolution Date]]-TODAY())
Overdue?2 = IF(ISBLANK(Issues[[#This Row],[Target completion date]]),"",IF(Issues[[#This Row],[Target completion date]]<TODAY(),"Yes","No"))
Overdue?27 = IF(ISBLANK(Issues[[#This Row],[Target completion date6]]),"",IF(Issues[[#This Row],[Target completion date6]]<TODAY(),"Yes","No"))
Overdue?28 = IF(ISBLANK(Issues[[#This Row],[Target completion date7]]),"",IF(Issues[[#This Row],[Target completion date7]]<TODAY(),"Yes","No"))
Note on U7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: add in forumla to make sure empty if no target resolution date
Note on Q8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: New mitigation. I have opened a recruitment for an FD, which will be the sixth Board member. Reply: new mitigation added
Note on Q9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Include a mitigation of the Task and Finish group. Reply: T&F added to resolution plan
Note on Q10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Needs a mitigation of the Task and Finish group. Reply: T&F added to resolution plan
Note on K12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The impending issue of Autumn 2022 contract end dates has been successfully mitigated Reply: I have updated the impact, removed the September issue and added the procurement resourcing bottleneck from Jan 2023 (Pipeline). I have asked Wayne to review whether this warrants a separate issue.

## Risks Report (hidden)
ID | Risk Name | Description | Impact Description | Owner | Response | Residual Risk Rating | Risk Rag (Progress) | Overdue? | Management Actions
R001 | Lack of clarity and strategy on data approach | If there is no agreement on the policy and technical priorities to standardise data sharing at a devolved level and/or there is insufficient governance and delivery capability to ensure that devolved services work in that context | 1) Then LI Ltd is not able to deliver replacement services or a comprehensive traceability service at a UK level. 2) LI Ltd data practice is not operating efficiently because it requires considerable time and cost to resolve data issues and maintain data quality. | Stuart McDonagh | Treat | Moderate | 1 | No | Secure agreement for common data standards and formats with the Devolved Administrations and DDTS as new species come into scope for England multi-species platform and UK View. Provision of data for UK View and share of operational data for cross border moves to be treated separately. LI Ltd have data for UK View but continue to work on ensuring consistency of data for cross border moves. Work being carried out on DSAs by Daniel Meaney (DPO) and Malcolm Dunsmore.
R002 | Implementation of project A delayed | There is a risk that the Livestock Information Transformation Programme (LITP) will not complete the design and implementation of BEID and digital passports in a sufficiently timely manner to align with new traceability service delivery. | This will lead to LI having to implement multiple tags (old tags and BEID), both paper and electronic passports, that would cause negative reputational impact for Defra, AHDB and LI Ltd and drive cost into the solution. | Simon Freeman | Transfer | Low | 1 | No | 1) LI need Policy to move faster on all aspects of requirements, including BeID, Digital Passports and Automated Moves. 2) Working with the LTP Design Authority on data issues. 3) Awaiting confirmation that all cattle legislation will be complete by March 2024.
R003 | Lack of effective decision-making | If the decision-making authority is unknown or unclear at the Livestock Transformation Programme Board (LTPB) because Members of the Company (AHDB/Defra) have not clearly defined the Scheme of Delegation. | Then key decisions are slow or cannot be made and LI Ltd is unable to deliver its strategic objectives. Resulting delay in next steps - bEID, Digital Passports and Automated Moves. Members do not agree with the Target Operating Model (as set out in the Delivery Agreement). There is duplication or work of little or no consequence/value. The delegated authorities, accountabilities and responsibilities of LI Ltd's Senior Leadership Team are unclear. The worst case could result in a terminal outcome for the programme or LI Ltd due to the inability to fulfil its strategic objectives. | Ian Hewett | Treat | Critical | 3 | Yes | 1) John Cross and Ian Hewett consider refreshing the GOM and DA after the review of the company's sponsorship model concludes. 2) Prioritise input into the LTPB, focussing on teasing out direction and requirements and establishing an effective working relationship. 3) Ian Hewett presented to the LTPB the decisions required of it and use those to inform learning about who makes what decision and on what basis. 4) Implement findings / recommendations of the task and finish groups. 5) New SRO (Vicky Moore) establishing structure 6) Established regular joint SLT meetings
R004 | Key permanent staff or any staff with specialist skill leave. | Key permanent staff or any staff with specialist skill leave. | Then this may result in a negative impact on operational running and delivery, cost overruns, time delays, and failed procurement due to a lack of resilience. The worst case could result in a terminal outcome for the programme or LI Ltd because of delivery failure. | Stuart McDonagh | Treat | Critical | 3 | Yes | 1) Diversify LI Ltd’s approach to staff recruitment and retention. 2) Manage critical knowledge by documenting activities, identifying others for training and knowledge transfer and undertaking succession planning for key skills. 3) Create a great place to work, a supportive and inspired culture where delivery professionals feel empowered. 4) Undertake skills and services audit and establish the gaps. 5) Development of a new Target Operating Model including a Human Capital Management capability. 6) LI in process of creating baseline set of LI's own corporate HR policies, based on AHDB documentation by 31/03/23 7) Provide LI specific wording to fit into AHDB's templates for JD's 8) Tactically deploying PMO resources across the TOM pillars
R005 | Lack of resilience against unexpected disasters and events | If LI Ltd is not prepared for a variety of threat scenarios that lead to damage to, or loss of, key resources or core assets, for example, cyberattacks, data breaches, unplanned IT outages, security incidents, loss of 3rd party location, loss of key personnel. | Then LI cannot restore the Livestock Information Service to a predefined level of operation following a disruption that may fail to deliver the core statutory service or result in a loss of essential data, which affects its reputation negatively. The worst-case could result in a terminal outcome for the programme or LI Ltd. | Stuart McDonagh | Treat | Moderate | 1 | Yes | 1) Complete remaining disaster recovery testing (as per IT Control Audits action) 2) Commission a test of the BCP in early 2023. 3) QA Lead to take lead on progressing a proper level of robustness in documents and policies. Work was initiated to establish criteria for National Infrastructure and Critical National Infrastructure and where LI systems sit in these definitions so we can incorporate appropriate RTO/RPO into the future design. 4a) Current state: COO coordinating BC and DR responses. 4b) Future state: Programme coordinating design and operations activities to ensure the service integration model is correct i.e. that BC, DR, security and monitoring are built in from day one. 5) Appoint a security/cyber partner to reinforce remedial actions
R006 | Failure to manage key commercial partnerships, and contractual requirements | If LI LTD fails to manage key commercial partnerships and contractual requirements | Then funding is not approved or does not provide the certainty needed to enter complex commercial agreements. Key contracts reach the end of life without commercial arrangements to extend or renew. The spending trajectory of key contracts exceeds the maximum contract value in place of new commercial arrangements. Which may result in short-sighted commercial decisions, poor performance, inefficiency, poor value for money, fraud, and /or failure to meet business requirements/objectives. | Stuart McDonagh | Treat | Moderate | 1 | Yes | Define future sourcing model. Dependency on the findings/recommendations of the task and finish group which informs commercial pipeline and Contract management. Define commercial pipeline Document approach to Contract Management
R007 | Delivery partner contracts expire before replacement arrangements are in place | If LI are not able to put suitable new or replacement arrangements in place before current contract expire(s) | Then LI may be forced to extend the current arrangements as a Direct Award which places a risk on continued compliance with the Procurement Regulations and may give rise to an increase in current prices and/or introduction of new terms which may be difficult to successfully mitigate or avoid | Stuart McDonagh | Treat | Severe | 1 | Yes | 1. Livestock Transformation Programme Board to begin planning now for funding arrangements and spend controls approval for future years. 2. Contracts requiring extension/renewal beyond FY22/23 to be flagged to SRO by LI MD with a recommendation to extend or replace based on current knowledge of delivery landscape.
R008 | Rework of the requirements specification in response to various design reviews | If LI view of the current specification of requirements for Cattle need to be amended following the outcomes of the strategic review and completion of current Defra cattle design projects. | Then there is a risk that delivery plans will need to be impact assessed and changes made to the delivery scope, timing and priority. | Simon Freeman | Transfer | Critical | 3 | Yes | 1) LI Ltd to continue to engage with key stakeholders to secure emerging ensure early view of plans and scope for initial cattle delivery. 2) LI Ltd to continue to take a flexible approach to building the backlog and ensure flexibility within third party contracts to enable re-allocation or termination of resource if required due to a substantive change in requirements and/or direction.
R009 | Obligations under company law | If Members of the Company (AHDB/Defra) are unable to provide a stable board with long-serving and committed members. | Then the Board is unable to provide effective governance in relation to its obligations under Company law. Creates risk to the overall control & delivery environment. | John Cross | Transfer | Moderate | 1 | Yes | Board Chair to escalate to Members of the Company (AHDB/Defra)
R010 | Reputational Damage | Industry and wider stakeholder expectations regarding delivery of the multi-species service [platform] are not met. | Industry, suppliers, and staff loose confidence in the strategy, objectives and plans of the Defra Livestock Information Transformation Programme (LITP) and through that, LI Ltd. Industry support for LI Ltd and the intended outcome wanes. Suppliers disengage and key staff leave. | Ian Hewett | Treat | Severe | 2 | No | 1) Secure future funding from LTPB 2) Secure go ahead for Cattle delivery from LTPB 3) Use communication channels of TDUG and Defra/AHDB sponsors to mitigate any damage caused.
R011 | Fraud | If LI systems are subverted or fraudulent entries accepted. | Then the quality and traceability of livestock may be compromised, increasing the likelihood of chronic endemic livestock diseases becoming prevalent, and reducing consumer confidence in the provenance of British meat and livestock products. | StuartMcDonagh/Simon Freeman | Transfer | Moderate | 1 | No | 1) Engaging with James Couzens in Defra Food Security (Sector Cyber Strategy Lead Defra, and NCSC). 2) Putting in place a Fraud Strategy covering both fraud risk within LI and industry fraud.
R012 | Temporary staffing | IF inappropriate payments are made to staffing agencies, | THEN value for public money will not be achieved. | Stuart McDonagh | Treat | Moderate | 1 |  | No gaps in control identified
R013 | Working elsewhere on Company time | IF an employee works for another employer on LI Ltd time, by reporting sick when they are actually fit for work, or otherwise, | THEN productivity will be lost and there may be a failure to achieve other corporate objectives., and may incur additional cost to cover those duties. | Stuart McDonagh | Treat | Moderate | 1 |  | Implement Declaration of Interest policy?
R014 | FBR5: Declarations of interest | IF staff fail to properly manage conflicting interests, | THEN these may be exploited for personal gain resulting in failure to achieve value for public money and giving rise to an impression of impropriety amongst members of the public. | Stuart McDonagh | Treat | Severe | 2 |  | Implement Declaration of Interest policy? Implement CoI process?
R015 | Mandate fraud | IF unauthorised bank accounts are set up or unauthorised amendments are made, | THEN monies could be diverted to criminals instead of being paid to genuine supplier accounts. | Stuart McDonagh | Treat | Severe | 2 |  | 0
R016 | Ghost employees | IF ghost employees or duplicate payments are added to pay runs, | THEN fraudulent payments may be made. | Stuart McDonagh | Tolerate | Moderate | 1 |  | NA
R017 | FBR9: Changes | IF grading for an employee is changed fraudulently, | THEN an employee could receive additional income they are not entitled to and value for public money will not be achieved. | Stuart McDonagh | Tolerate | Moderate | 1 |  | NA
R018 | Leavers | IF former employees remain on the payroll and continue to receive payment, | THEN an employee could receive additional income they are not entitled to and value for public money will not be achieved. | Stuart McDonagh | Tolerate | Moderate | 1 |  | NA
R019 | Expenses | IF fictitious or false claims are submitted by employees and paid, | THEN an employee could receive additional funds they are not entitled to and value for public money will not be achieved. | Stuart McDonagh | Tolerate | Moderate | 1 |  | NA
R020 | Invoice fraud | IF duplicate, inflated, inaccurate or fake invoices are paid, | THEN this can result in failure to achieve value for money or direct loss of public funds. | Stuart McDonagh | Treat | Moderate | 1 |  | Implement CoI process?
R021 | Direct debit or bank transfers | IF unsuitable individuals gain access to account information, | THEN unauthorised transfers or spends may be made from LI Ltd bank accounts via the setting up of direct debits. | Stuart McDonagh | Tolerate | Moderate | 1 |  | No gaps identified
R022 | Procurement | IF LI Ltd fails to control and manage procurement processes, | THEN these may be manipulated or subverted by internal actors or by external collusion, enabling the creation of ghost suppliers or contracting with unsuitable suppliers, resulting in direct fraud losses or failure to achieve best value for public funds. | Stuart McDonagh | Treat | Moderate | 1 |  | Implement Single Tender Waiver Policy
R023 | Lack of effective contract and supplier management | If LI fails to effectively manage contract deliverables, LI obligations, and supplier obligations as set out in contractual agreements | Then i) Value realisation under the contractual agreements may not be achieved resulting in poor performance and/or poor value for money; ii) Wider delivery objectives may not be met; iii) Compliance issues may arise where contract values or durations are greater than originally stipulated; iv) Risk of fraudulent activity increases; v) LI may be forced to extend incumbent arrangements or award new contracts on a Direct Award basis which may give rise to an increase in current prices or introduction of new terms which may be difficult to successfully mitigate or avoid. | Stuart McDonagh | Treat | Moderate | 1 | Yes | 1. Contract management processes to be developed based on CCS 'Bronze' 'Silver' and 'Gold' tiering levels; 2. Contract register to be regularly updated to include a review of contract end dates and trigger dates for review; 3. Commercial pipeline to be developed (and updated as necessary subject to outputs from the strategic review) which links expiry of contracts with plans to procure and implement replacement arrangements; 4.Livestock Transformation Programme Board to begin planning now for funding arrangements and spend controls approval for future years. 5.Contracts requiring extension/renewal beyond FY22/23 to be flagged to SRO by LI MD with a recommendation to extend or replace based on current knowledge of delivery landscape.
R024 | Lack of funding or support for run and maintain activities | If LI is not provided adequate funding then progress on a fully effective multi-species service will stall. | LI no longer becomes viable, the service will either cease or need to be transferred (novated) to another organisation resulting in significant delays. If no funding is provided or funding levels are too low then a fully effective multi-species service will be delayed and over a longer period resulting in delays to the benefits realisation. | Ian Hewett | Treat | Critical | 3 | No | 1) LITP secured 7 months funding to the end of September 2023 2) Confirmation that LI run and maintain cost is included in the annual business planning cycle.
R025 | Scoteid review may delay the current roadmap of delivery | The Defra Livestock Information Transformation Programme Board (LTPB) has requested a review of the suitability of ScotEID as a potential solution for LI to build the next phase of multi-species and cattle. The proposal is to have DDTS undertake the review. | There are a number of impacts. Firstly, the review itself will take time and it is unclear whether progress can be made in LI until that option is considered. Should LI be asked to wait for an outcome, the current plans and spend forecasts will no longer be valid and new ones will be need post review should the outcome be to move to Scoteid. The second impact is linked to the outcome. Should DDTS determine that ScotEID is the solution, LI will have a technical solution imposed upon it that it will not have done any due diligence on. Furthermore, the accountability for the solution would need to sit with DDTS rather than LI until a time when LI could undertake its own due diligence on the solution. Should SCoteid be put as the future solution, a full impact assessment would be needed to ascertain the gap between current functionality (the scottish solution) and the future processes and policies in England that would need to be implemented. A full assessment by LI could take 3 to 6 months before any plans or costs could be committed to. This will result in significant delays to the cattle implementation and it would be unclear whether budgets could be forecast ahead of the Q4 22/23 period when investment for future years would be decided. | Simon Freeman | Treat | Severe | 2 | Yes | 1) The proposal is to limit the ScotEID review to a brief technical consideration based upon the Welsh feedback that it is not a suitable platform upon which to build. 2) Having Wales already discounted the solution, the review should consider the ratification of the Welsh view (on the ScotEID technology) rather than a full stand alone review.
R026 | Head of Finance departure and lack of Finance Director | If the HoF leaves and LI does not have a Finance Director | Then LI is without adequate financial goverance and control that increases the risks of compliance failure, of fraudulent activity, failure to meet obligations under company law. Creates risk to overall control and delivery environment. | Ian Hewett | Treat | Moderate | 2 | Yes | Recruitment of Finance Director and adequate succession planning.
R027 | Delays to legislative changes | The requirement to change legislation to alter industry behaviours delays delivery of the multi-species data service |  | Ian Hewett |  | Severe | 3 | Yes | 0
R028 | Regulation changes delay the live deployment dates | The time it will take to change and implement legislation that supports movements and traceability could cause delays to the live dates of the new solutions | Delays to legislation would mean key transformations such as BEID and passport removals cannot be implemented ahead of predicted legislation March 25. This will mean we either implement passports and go live in MVP or have to not include the cost of implementing passports and delay any go live (MVP) beyind March 25 | Simon Freeman | Treat | Severe | 2 | No | Work with policy to identify ways to go live early through bringing forward legislation or enable early go live with legislation to follow.
R029 | RPA customer service centre industrial action | If strike action in the customer service centre proceeds it will have a significant impact on RPA operations ability to administer the work of the RPA at a critical time of year. | Could impact LUIS (SM) and CTS (SF) and delay handover of bureau service | Stuart McDonagh | Tolerate | Low | 1 | Yes | 1) According to BCMS any proposed strike won't impact cattle go-live or the LUIS service. 2) LI have almost completed UAT, and model office / training happen after the strike ends. 3) Most project work is paused during the Christmas break.
R030 | Procurement resourcing bottleneck | Insufficient commercial capacity to deliver and manage required commercial arrangemnents in the short term | Dependency on commercial activity may be a blocker for timely programme delivery and progressing corporate objectives if commercial arrangements cannot be put in place when needed. | Karen Dobson | Treat | Severe | 2 | Yes | 1) 'Procurement as a Service' contract in place with Cadence Innova would enable extra commercial capacity to be used on a project-by-project basis; 2) Review planning and sequencing of commercial pipeline activities to ensure priorities align to outline programme delilvery plans and corporate commitments.
R031 | risual struggling to deliver contracted services | risual do not have the internal capabilities, practices, repeatable processes, and competencies for the services contracted. | Impeding maturity of LI service, slow to implement new enhancements, delays to DR testing and documented incident response plans. Maturity of SOC and cyber response. | Stuart McDonagh | Treat | Moderate | 1 | No | Strategic direction and LI Future Mode of Operation (FMO). 1. Insource Service Desk and Service Management Practices (Paul H leading) 2.Procure IT Operations / Azure Platform to align to riusal contract end point 14/11/23 (Paul W leading) 2.Procure SOC as a Service and Cyber Incident Response specialism to align to riusal contract end point 14/11/23 (Paul W leading)

## Issues Report (hidden)
ID | Issue Name | Description | Impact Description | Owner | Response | Issue Rating | Issue Rag (Progress) | Overdue? | Management Actions
LI-I071 | Customer requirements are incomplete | No agreed customer requirement for cattle that maps from outcomes through risks and needs, encompassing regulatory and business process requirements. | Inadequate decision-making landscape for solution design. LI Ltd is unable to measure service and programme delivery progress against the requirement. | Defra | Transfer | Critical | 3 | Yes | LI Ltd to continue to set out what it requires from Members of the Company to inform cattle sprint 0. Work proactively with colleagues to help shape/inform the requirement as required. If necessary, slow down delivery if the requirement is not sufficiently clear, setting out the consequences of doing so.
LI-I073 | Member direction and involvement | LI Ltd does not have stable board membership from company Members on its Board. LI Ltd does not have the authority to ensure that the board is equipped with the skills required to ensure effective company oversight. | Regular changes weaken relationships and trust and reduce the understanding of company mission, structure and associated rationale. Weakens LI Ltd.'s overall influence and ability to drive collaborative delivery. | AHDB/Defra | Transfer | Severe | 2 | Yes | 1) The UK CVO has become the Defra member on the Board. 2) An FD has been recruited and is the sixth Board member (from the seven Board positions). 3) Invest in relationships through Defra Livestock Transformation Programme Board LTPB. 4) Clarify Defra input into the LI Board and associated governance. 5) Self assessment evaluation conducted and findings reviewed with the Chair. 6) Defra and AHDB sponsors are currently considering changes to sponsorship of the company, with the expectation that Defra becomes the major shareholder. Once confirmed the sponsorship changes are expected to result in changes to the Board and Audit and Risk Committee.
LI-I074 | LI Ltd Governance | Lack of clarity with regard to the role of the board and its delegations. Insufficient definition of LI governance structure within the Livestock Transformation Programme Board governance to provide clearly articulated roles, decision making, and delivery oversight functions. | Duplicative and conflicted governance creates overhead and distracts from delivery/decision making. Creates lack of clarity as to which decisions are within LI senior team delegations. Erodes trust and reduces confidence. Contributes to blame culture and poor job satisfaction | AHDB/Defra | Transfer | Critical | 3 | Yes | 1) LI Ltd Board has requested a revised version of the GOM, highlighting areas needing clarification. 2) LI Ltd Board and subcommittees to be confirmed/redefined once Defra and AHDB have concluded proposed changes to the company's sponsorship. 3) LI Ltd MD to develop a decision making framework for consideration at the LTPB.
LI-I076 | LI Ltd Governance | The Governance Operating Manual and Delivery Agreement are now out of date because Members of the Company (AHDB/Defra) have changed the governance landscape. | Accountabilities, responsibilities and delegations for decision making between the LI Board, the LTPB and LI Ltd are not known or are out of date. Decisions could be taken without relevant authorisation or not taken at all. | AHDB/Defra | Transfer | Severe | 2 | Yes | 1) Refreshing delegated authorities, accountabilities, and responsibilities of LI Ltd from AHDB/Defra in an updated GOM and Delivery Agreement following review of the company’s sponsorship model. 2) LI Ltd MD has produced and circulated a version of the GOM highlighting the areas for revision (e.g. AO and FD responsibilities). 3) LI Ltd MD to update the GOM based on the outcome of the Defra convened task and finish group that looks at sponsorship and corporate affairs to take forward recommendations of the Cabinet Office Review.
LI-I077 | Loss of key individuals | Loss of Programme Director and COO | Negative inpact on operational running and delivery, time delays, and concerns over the efficacy of the procurement and the ability to successfully transition to replacement arrangements absent a Programme Director | Ian Hewett | Treat | Critical | 1 | Yes | Simon Freeman recruited and expected to join in early September as Programme Director. Recruitment of a replacement COO is underway
LI-I078 | Lack of confirmed funding for subsequent fiscal years | Absence of medium and long term funding and/or SRO instruction to proceed. | LI will lose staff if we cannot forward commit beyond September 2023. The ability to pay staff (employees and contractors) is also at risk. | Vicky Moore | Transfer | Severe | 2 | Yes | 1) Funding confirmation for BAU work has been confirmed by the LITP SRO. 2) A closure report for the sheep service was approved by Defra Investment Committee (7th Sep 22), providing financial authority for the remainder of the last financial year, and an expectation that LI Ltd will bid for BAU funding for future years. 3) The issue of contract termination notices for a suite of trigger points in September 2022 has been successfully mitigated. 4) Worsening situation on government financing. Leadership Team working on options and mitigating actions to counter a potential ask from the central government. Currently no commitment to future year funding for development beyond September 2023.
LI-I079 | Reputational Damage to LI Ltd and/or Defra | Industry and wider stakeholder expectations regarding delivery of the multi-species service [platform] are not met because delivery does not proceed at pace or beyond the live sheep service. | Industry, suppliers, and staff loose confidence in the strategy, objectives and plans of LI Ltd. Industry support for LI Ltd and the intended outcome wanes. Suppliers disengage and key staff leave. | Ian Hewett[/John Cross] | Treat | Critical | 2 |  | Secure future funding from Paul Caldwell/LTPB Secure go ahead for Cattle delivery from Paul Caldwell/LTPB
LI-I080 | DA Data problem is being dealt with bottom up | While the data movements are covered by agreements, there is no clarity or strategy on how data across the DAs will be handled and will flow. This cannot be handled from the bottom up as is currently the case. | Complex inter organisation data flows causing data quality issues and high cost of maintenance | Simon Freeman | Treat | Critical | 3 | Yes | 1) LI to work with Defra on the DA problem from top down to agree a strategy on who will do what in the data area across Das 2) Aiming to simplyfy the requirements of disparate data sharing agreements (between different countries, organisations and species). One overarching agreement is not achieveable. Proposal to take papers to the DA for the LTPB seeking to align behind a single agreement for each of England, Scotland and Wales containing variance. Data alignment being led by Roger Goodwin within LITP.
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
LI-I081 | LIS Data Retention | UK View Data Sharing Agreements with ScotEID and WG require data erasure. Review of DSAs in progress to add catlle to the exisitng Sheep, Goat and Deer agreements. The LIS has no process or procedure in place to manage data retention. Most other agreements are public task orientated with retention of data as long as is required. | Potential breach of agreements. DAs could decide to not share data if retention requirements are not met by the LIS. Data erasure could impact APHA reporting requirements/obligations. (Shows lack of holistic approach) | Malcolm Dunsmore | Treat | Severe | 2 | Yes | Addressed as part of LI-I081 providing a holistic understanding of data processing, including retention, across all organisations involved in livestock movement / disease traceability. Noting current guess, pre planning, is that Cattle data will be required for UK View c. end April 23.
LI-I082 | UK View DSAs with ScotEID and WG | Engagement from ScotEID on UK View DSA for Cattle has gone cold, post questioning if a DSA was actually required. The DSA is based on personal data and the LIS does not get Scottish PD from ScotEID data but rather from AMLS2 (moving to SAM in the future). Engagement from WG is intermitent. | It may not be possible to include Cattle data in UK View without ScotEID and WG DSAs agreed to. | Malcolm Dunsmore | Treat | Critical | 3 | Yes | Aiming to simplyfy the requirements of disparate data sharing agreements (between different countries, organisations and species). One overarching agreement is not achieveable. Proposal to take papers to the DA for the LTPB seeking to align behind a single agreement for each of England, Scotland and Wales containing variance. Data alignment being led by Roger Goodwin within LITP.
LI-I083 | Newline software sending duplicate movements | Issue 89508: Newline(market software) have had an issue where their software has been sending duplicated movements, this is causing down stream abattoirs/keepers problems as they have the same move many times. | Impact on Sheep Service | Graham Gosling | Treat | Severe | 2 | Yes | 1) CLA team have produced an extract of the duplicates and we are working through this and cases that have been raised with Newline. 2) Newline so far have been able to undo the duplicated movements and this rectifies the problem 3) We should consider comms to the abattoirs to explain the problem as they will see this as a problem with our LI service. 4) GG will speak to Sarah O about how we tackle this on 31st Jan. 5) In the mean time we are consolidating the list of market moves and getting Newline to fix.
LI-I084 | risual struggling to deliver contracted services | risual are struggling to deliver contracted services because they do not have the internal capabilities, practices, repeatable processes, and competencies for the services contracted. | Impeding maturity of LI service, slow to implement new enhancements, delays to DR testing and documented incident response plans. Maturity of SOC and cyber response. | Stuart McDonagh | Treat | Moderate | 1 | No | Managing commercial and operational mitigations pending the re-procurement. Strategic direction and LI Future Mode of Operation (FMO). 1. Insource Service Desk and Service Management Practices (Paul H leading) 2.Procure IT Operations / Azure Platform to align to riusal contract end point 14/11/23 (Paul W leading) 3.Procure SOC as a Service and Cyber Incident Response specialism to align to riusal contract end point 14/11/23 (Paul W leading)
LI-I085 | Key permanent staff or any staff with specialist skill leave. | Key permanent staff or any staff with specialist skill leaving because losing key people is inevitable. They may take a new job opportunity, retire, suffer a long-term illness, or die unexpectedly. | A negative impact on operational running and delivery, cost overruns, time delays, and failed procurement due to a lack of resilience. | Stuart McDonagh | Treat | Critical | 3 | Yes | 1) Diversify LI Ltd’s approach to staff recruitment and retention. 2) Manage critical knowledge by documenting activities, identifying others for training and knowledge transfer and undertaking succession planning for key skills. 3) Create a great place to work, a supportive and inspired culture where delivery professionals feel empowered. 4) Undertake skills and services audit and establish the gaps. 5) Development of a new Target Operating Model including a Human Capital Management capability. 6) LI in process of creating baseline set of LI's own corporate HR policies, based on AHDB documentation by 31/03/23 7) Provide LI specific wording to fit into AHDB's templates for JD's 8) Tactically deploying PMO resources across the TOM pillars
LI-I086 | Cash flow management | The inability of LI to generate invoices to Defra (in a format best suited to LI) in a timely fashion that enables LI to pay its suppliers in a timely fashion because of LIs reliance on AHDB. There is a very short time window after AHDB complete month end for LI to produce an invoice. This creates a single point of failure that can easily lead to delays. | LI is not in control of the timely payment of supplier invoices so any delay in AHDB process has a knock on effect and could delay payments to suppliers. | Shendi Keshet | Treat | Critical | 3 | Yes | Dependency on AHDB until such time as the AHDB sponsorship change has been completed and LI can develop a new service offering that aligns with its business practices.

## IF NEEDED Action Log (hidden)
Unique Task ID. This should be the functional area/project's unique 2 or 3 digit suffix, followed by 'T' for 'task', followed by a unique consecutive number beginning 001 - i.e. LI-A001 | Defines the short name for the task | The date this task has been identified. | Defines the resource responsible for verifying that the task is managed and tracked appropriately through its lifecycle | Specifies the progress of the task | Description of the task with sufficient information/detail for one to understand the matter. It should be written clearly such that it is meaningful for the target audience as determined by the Reporting Level. | Defines the likelihood that a Task will be completed. 1-4. (4:Very High 76- 100%; 3:High 51-75%; 2:Medium 26-50%; 1:Low <25%) | Defines the effect of the task on the project / programme objectives. scale of 1-4 (1 indicates a very low to low impact,4 indicates a high to very high impact). | Priority calculated by Probability and Impact | Assessment of the progress completing the task. On target (1), caution (2) or not on target (3) | Defines the date the task is targeted to be completed. | Defines the actual date the task is completed. | Updates on any change of status and the reason. It should highlight recently completed activities to transfer, mitigate or resolve the task. | IDs of Risks, which are directly associated with this task. | IDs of Issues, which are directly associated with this task. | IDs of Assumptions, which are directly associated with this task. | IDs of Dependencies, which are directly associated with this task. | Days until the task is due (calculated) | Is the task already overdue? (Calculated)
Task ID | Task Name | Date identified | Owner | Status | Description | Likelihood | Impact | Priority | Overall Task RAGs | Planned Completion Date | Actual Completion Date | Latest Update | Associated Risks | Associated Issues | Associated Assumptions | Associated Dependencies | Days until target date | Overdue?
TSK001 | Test 1 | 2021-10-01 | Test, Test | Closed | Test | High | Low | High | 3 | 2021-11-01 |  | This is a test update. | RSK0003 | ISS0002 | ASS001 | DEP001 | -688 | Yes
TSK002 | Test 2 | 2021-10-02 | Test, Test | Open | Test | Medium | Medium | Low | 2 | 2021-11-20 | 2021-11-19 | This is a test update. | RSK0004 | ISS0003 | ASS001 | DEP002 | -669 | Yes
TSK003 | Test 3 | 2021-11-01 | Test, Test | Open | Test | Low | Medium | Medium | 2 | 2021-11-04 |  | This is a test update. | RSK0005 | ISS0004 | ASS001 | DEP003 | -685 | Yes
Formulas:
Days until target date = Risks3[[#This Row],[Planned Completion Date]]-TODAY()
Note on J2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: need to add in rag

## IF NEEDED Assumptions (hidden)
Defines the short name for the assumption | The date this assumption has been identified. | Unique Assumption ID (e.g. ASS000) | Defines the resource responsible for verifying that the assumption is managed and tracked appropriately through its lifecycle | Specifies the progress of the assumption | Updates on any change of status and the reason. It should highlight recently completed activities to transfer, mitigate or resolve the assumption. | Description of the assumption with sufficient information for one to understand the matter. It should be written clearly | Detailed impact description of the assumption on the project objectives (scope, schedule and budget). High priority items should detail impact to external regulatory compliance where applicable | Date when assumption will be realized/ missed. | Defines the likelihood that an assumption will occur. (High: > 70%; Medium: 30-70%; Low: <30%) | Defines the effect of assumption on the project / programme objectives. | Overall rating of assumption (defined by Impact and Prority) | IDs of risks, which are directly associated with this assumption. | IDs of issues, which are directly associated with this assumption. | IDs of assumptions, which are directly associated with this assumption. | Days until the Assumption impact date (calculated) | Is the Assumption overdue? (calculated)
Assumption Name | Date identified | Assumption ID | Owner | Status | Latest Update | Description | Impact Description | Impact Date | Probability | Impact | Overall Assumption RAG | Associated Risks | Associated Issues | Associated Assumptions | Days until impact date | Overdue?
Test | 2021-11-08 | ASS0001 | Test, test | Open | This update is just a test update. | Test | Test | 2021-12-18 | Medium | Medium | Green | RSK0001 | ISS0003 |  | -641 | Yes
Formulas:
Days until impact date = Assumptions[Impact Date]-TODAY()

## Data_Risks
General |  |  |  | Details |  |  |  |  | Quantify Risk |  |  |  | Resolution |  |  |  | Actions |  | Appetite
RiskName_FieldLength | Status_Options | RiskCategory_Options | LatestUpdate_FieldLength | Description_FieldLength | ImpactDescription_FieldLength | ImpactDate | Assumption_FieldLength | Escalation_Options | Likelihood_Options | Impact_Options | Risk_Velocity | Risk RAG | Resolution/Mitigation_FieldLength | TargetResolutionDate | ActualResolutionDate | ResponseType_Option | Action RAG | Status_Options | Appetite_Options
100 | Open | Commercial | 2000 | 400 | 1000 |  | 1000 | ADPG | Very Low | Very Low | Slow | 1 | 1000 |  |  | Treat | 1 | Open | Averse
| Closed | Data | not to be used |  |  |  |  | AHDB | Low | Low | Medium | 2 |  |  |  | Terminate | 2 | Closed | Minimal
|  | Delivery | [5 empty] | Defra | Medium | Medium | Fast | 3 |  |  |  | Transfer | 3 |  | Cautious
|  | Financial | [5 empty] | LI Board | High | High | [5 empty] | Tolerate |  |  | Open
|  | Governance | [5 empty] | LI Chair | Very High | Very High | [8 empty] | Eager
|  | Operations | [5 empty] | LTPB
|  | People | [5 empty] | SRO | Risk Matrix
|  | Process | [5 empty] | NA | Impact |  | Very Low | Low | Medium | High | Very High
|  | Technology | [6 empty] | Probability | Very High | Severe | Severe | Critical | Critical | Critical
[10 empty] | High | Moderate | Moderate | Severe | Critical | Critical
[10 empty] | Medium | Low | Moderate | Moderate | Severe | Critical
[10 empty] | Low | Low | Moderate | Moderate | Moderate | Severe
[10 empty] | Very Low | Low | Low | Low | Moderate | Moderate
[11 empty] | 1 | 2 | 3 | 4 | 5
[10 empty] | 5 | 5 | 10 | 15 | 20 | 25
[10 empty] | 4 | 4 | 8 | 12 | 16 | 20
[10 empty] | 3 | 3 | 6 | 9 | 12 | 15
[10 empty] | 2 | 2 | 4 | 6 | 8 | 10
[10 empty] | 1 | 1 | 2 | 3 | 4 | 5

## Data_Assumptions
Status_Options | AssumptionReportingLevel_Options | ProbabilityToMiss_Options | Impact_Options | OverallAssumptionRAG
Open | CxO Reporting | Low | Low | Green
Closed | Management Reporting | Medium | Medium | Amber
| Programme Level | High | High | Red
Project Level

## Assumptions
Give each assumption a unique ID so that it can be tracked easily and cross referenced. | Enter the category of the assumption. This category will likely be specific the project industry/type so no suggestions are provided here. If a category is not needed this Field can be changed or removed. | A clear description of the assumption or constraint. For example 'it is assumed that the internal training team will deliver the administrator training'. | The individual responsible for ensuring that the assumption is validated in the agreed upon manner. | The date the assumption is need to be validated or is expected to be validated. | Document the actions that need to be carried out to validate the assumption. Include any updates needed to other project documentation for example the Project Charter, Issue Log and Risk Register. | The status of each assumption. For example, Open (not yet validated), Not valid (the assumption is not correct), Valid (this assumption is valid). | Add any relevant comments here. For example, follow-on actions for assumptions that are not valid. In these cases it may be necessary to review the business case, project charter, risks, issues etc.
ID | CATEGORY | DESCRIPTION OF ASSUMPTION/CONSTRAINT | RESPONSIBLE PARTY | DUE DATE | ACTIONS TO VALIDATE THE ASSUMPTIONS | STATUS | COMMENTS
A001

## Data_Issues
General |  |  |  |  | Details |  | Quantify Issue |  |  | Resolution |  |  |  | Action
IssueName_FieldLength | Status_Options | IssueCategory_Options | LatestUpdate_FieldLength | Escalation_Options | Description_FieldLength | ImpactDescription_FieldLength | Issue_Options | Priority_Options | OverallIssueRAG_Options | Resolution/Mitigation_FieldLength | TargetResolutionDate | ActualResolutionDate | ResponseType_Option | Status_Options | Action RAG
100 | Open | Commercial | 2000 | ADPG | 400 | 1000 | Very High | Very High | 1 | 1000 |  |  | Treat | Open | 1
| Closed | Data |  | AHDB |  |  | High | High | 2 |  |  |  | Terminate | Closed | 2
|  | Delivery |  | Defra |  |  | Medium | Medium | 3 |  |  |  | Transfer |  | 3
|  | Financial |  | LI Board |  |  | Low | Low |  |  |  |  | Tolerate
|  | Governance |  | LI Chair
|  | Operations |  | LTPB
|  | People |  | SRO |  |  | Issue Matrix
|  | Process |  | NA |  |  | Impact |  | Low | Medium | High | Very High
|  | Technology |  |  |  |  | Probability | Very High | Severe | Critical | Critical | Critical
[8 empty] | High | Moderate | Severe | Critical | Critical
[8 empty] | Medium | Moderate | Severe | Severe | Critical
[8 empty] | Low | Moderate | Moderate | Severe | Severe

## Decisions
Give each decision a unique identifier or reference so that it can be easily traced. | Categorise the decision type. Commercial Data Financial Governance People Process Technology | Describe the decision, the context, and impact. Include details of any related changes, for example updates required to the project schedule, creation or approval of a change order, follow-on actions to be taken etc. | Record the person or group which made the decision. For example, the SLT, project or programme board. | Record the date the decision was made. It may also be worth recording where it was made, for example, in 14 October SLT, LTPB etc. | Note down any other useful information. For example, alternatives considered, the reason for the final decision and any related documentation (meeting minutes, background information).
ID | CATEGORY | DECISION | RESPONSIBLE PARTY | DECISION DATE | COMMENTS
D001 | Delivery | Design Authority signs off conceptual design (see minutes of DA meeting for evidence) | Design Authority | 2023-02-09 | Attended by: Gill Moger (GM) Roger Goodwin (RG) Chris Thornton (CT) Elaine Kendall (EK) Angela Drummond (AD) Simon Freeman (SF) Chris Moore (CM) Terry Gadd (TG) Warwick Ashburner (WA) David Painter (DP) John Lucey (JL) Tom Lewis (TL) Craig Kinloch (CK) Idaros Mohammed (IM) Jayne Spain (JS) Michael Anderson (MA) Emil Mcbrierty (EM) Chris Jordan
D002 | Delivery | Scope for LI to deliver is Cattle, Sheep, Pigs with equine and poultry to follow. Knowledge based trading and registration also included. | Seniors Meeting | 2023-02-14 | Those present Ian Hewett, Vicky Moore, John Cross, Elaine Kendall, Gill Moger

## Dependencies
Give each dependency a unique ID so that it can be tracked easily and cross referenced. | A clear description of the dependency. Any event or work that is either dependent on your project's result or on which your project will depend. |  | which delivers the task or milestone |  | which needs the task to be delivered
RECIPIENT DRIVES THE DEPENDENCY PROCESS
ID | Description | Impact of delay or change | SOURCE Workstream/ Function/ Department/ Programme/ Project | SOURCE Owner | RECIPIENT Workstream/ Function/ Department/ Programme/ Project | RECIPIENT Owner | SOURCE Due Date | SOURCE Forecast Date | Status (RAG) | Status (Open/ Closed) | Comments | Escalate Yes/No
DP001